FP6-016362

HY-PROSTORE

Improvement of the S&T research capacity of TUBITAK MRC IE

in the fields of hydrogen technologies

SSA

6-1. Sustainable Energy Systems

## Publishable final activity report

Period covered: from  01/05/2007 - 30/04/2008		Date of preparation:15.06.2008

Start date of project: 01.05.2005  				Duration: 36 months

Project coordinator name : Dr. Atilla ERSOZ

Project coordinator organisation name :

TUBITAK Marmara Research Center Energy Institute		Revision [Draft ]

1. Project execution

The strategic objective of the proposed project is to improve the research capacity of the center on hydrogen technologies (herein referred to as the “Center”) at TUBITAK MRC Institute of Energy (IE). Specifically, the Center aspires to improve its research capacity in the areas of hydrogen production, purification, and storage. The project is relevant to European Commission’s Priority Thematic Area 6-1, Sustainable Energy Systems.  According to the Work Programme for this thematic area, the scope of the proposed project can be seen as relevant to two sections in particular – Section 6.1.3.1.3 (Alternative motor fuels) and Section 6.1.3.2.2 (New technologies for energy carriers/transport and storage, in particular hydrogen).

There was only one contractor, as TUBITAK, in this specific project. The approach for accomplishing the project objective has multi-faceted. The approach includes: upgrading and renewal of related laboratory equipment; participation in international conferences; coordination of national&international brokerage events to enhance the participation in the FP6/FP7 project proposals within Turkey and EU; advisory board meetings between the Center and MS/ACC organizations to identify joint research activities; training courses for appropriate Center personnel on select hydrogen technology topics; and technical visits to and short-stays at hydrogen laboratories abroad.

In effort to accomplish the strategic objective, the Center has established the following specific objectives:

- upgrading and renewal of S&T equipment in hydrogen laboratories, including hydrogen production, purification and storage equipment, to improve the existing laboratory infrastructure;

- participation in international conferences and workshops, in order to network with researchers studying hydrogen technologies in other countries and to provide and obtain relevant scientific information;

- preparation of brokerage events for the relevant organizations and individuals from Turkey and European countries (including those from industry, academia, and government), which will allow to enhance the participation in the FP6/FP7 project proposals on hydrogen technologies;

- coordination of advisory board (AB) meetings between the Center and the relevant organizations in Europe to identify joint hydrogen research topics and activities of priority concern, which will maximize potential research benefits due to cooperative research and, likewise, will support efficient use of material and human resources;

- training courses for appropriate Center staff on hydrogen fundamentals, production, purification and storage, in order to expand the knowledge and capabilities of the Center’s hydrogen research scientists;

- technical visits to hydrogen laboratories at universities and other organizations in Member States (MSs) and Associated Candidate Countries (ACCs), in order to collect information about selected operating laboratory systems, share relevant information, participate in and observe experiments for information-sharing purposes, and develop ideas for future joint research projects and activities; and

- short stays at hydrogen laboratories in MSs and/or ACCs for young researchers from the Center, organized to provide hands-on experience with the laboratory practices and new technologies of the visited organization and to promote joint/cooperative activities between laboratories.

Specific impacts of the project have been realized during the project. These are as follows:

- Existing laboratory infrastructure at the Center has been improved, physically allowing the Center to expand its depth and scope of research in the future.

- Through specially developed courses, hydrogen researchers have also received training to further expand the knowledge base and capabilities of the Center.

- Several activities – such as international conferences, brokerage events, and technical meetings/visits –assisted in developing strategic networks and partnerships with both private and public institutions in Turkey and in Europe.

- Further, international conferences have been ensured the Center’s researchers are up to date on recent developments in related hydrogen topics, while also offering opportunities to share new study data from the Center.

- In fact, the project served as the main driving force for the dissemination of knowledge between European countries and Turkey for the near future.

- International/National brokerage events  promoted to enhance the participation in the FP6/FP7 project proposals on hydrogen technologies;

- AB (Advisory Board) meetings with organizations in the EU, along with technical visits to and short stays at laboratories abroad, supported the development of future joint/cooperative research activities and projects through the EC Framework Programmes.

- Technical visits to laboratories abroad also promoted information sharing on a detailed level, regarding laboratory equipment and experimental procedures.

- Finally, short stays provided extensive hands-on experience with new laboratory practices and technologies at the visited organization, increasing the knowledge and potential of the Center’s hydrogen researchers.

The project activity planning has bee given in the following table.

Management activities

WP1 Project management

Activities Specific for the Support Action

WP2 Renewal and upgrading of S&T Equipment

WP3 Conferences

WP4 Brokerage events

WP5 Advisory Board (AB) Meetings

WP6 Courses

WP7 Technical visits

WP8 Short stays

Work performed- Full duration of the project

1st period (01.05.2005 – 30.04.2006)

| WP no: | Work performed | Starting date | End date | Contribution to WP, % |
| --- | --- | --- | --- | --- |
| 2 | T.2.1.Purchasing for upgrading of hydrogen production equipment (2005) T.2.2.Purchasing for renewal of hydrogen purification (PSA) equipment (2005) T.2.3.Purchasing for renewal of hydrogen storage equipment (2005) | 01.06.2005 01.10.2005 01.05.2005 | 16.05.2006 13.03.2006 Scheduled July 2006 | 100 |
| 3 | T.3.1. International Hydrogen Energy Congress &Exhibition (IHEC 2005), 13-15 July 2005, Istanbul T.3.2. 2nd European Hydrogen Energy Conference (EHEC), 15-18,Nov.2005, Zaragoza, SPAIN | 13.07.2005 22.11.2005 | 15.07.2005 25.11.2005 | 100 |
| 4 | T.4.1. “Seminar on hydrogen technologies” , 2005/2006, 3 days, TURKEY | 12.04.2006 | 13.04.2006 | 100 |
| 5 | T.5.1. Kick-off meeting of the project, TURKEY T.5.2. Organizing the AB meeting on hydrogen production technologies based on reforming, 2005/2006- Gebze/Kocaeli | 19.09.2005 14.04.2006 | 19.09.2005 14.04.2006 | 100 100 |
| 6 | T.6.1. Course on Hydrogen fundamentals and hydrogen safety | Scheduled to Between 05.06.2006 and 07.06.2006 | Scheduled to Between 05.06.2006 and 07.06.2006 | 100 |
| 7 | T.7.1. Technical visit on hydrogen fundamentals hydrogen production technologies based on reforming, | 06.02.2006 | 10.02.2006 | 100 |
| 8 | T.8.1. Short Stays on Fuel reforming technology | 1 Researcher Scheduled between 05.06.2006 and 07.06.2006 (IFE) 2 Researchers Scheduled between 19.06.2006 and 15.07.2006 (CNR-ENEA) | 1 Researcher Scheduled between 05.06.2006 and 07.06.2006 (IFE) 2 Researchers Scheduled between 19.06.2006 and 15.07.2006 (CNR-ENEA) | 100 |

2nd period (01.05.2006 – 30.04.2007)

| WP no: | Work performed | Starting date | End date | Contribution to WP, % |
| --- | --- | --- | --- | --- |
| 1 | The First European Summer School on Hydrogen Safety (ESSHS) at the University of Ulster (Belfast, UK) from 15-24 August 2006. STORHY Project, Eurocourse Train-IN 2006 “Hydrogen Storage Systems for Automotive Application”, University of Applied Sciences Ingolstadt, 25-29 September 2006, Ingolstadt/Germany. “Third General Assembly (GA'06) and Exhibition/ Demonstration Event 2006 "From Strategy to Action: Timeline 2015", 4-6 October 2006, Brussels FP7 Information and Brokerage Day - Hydrogen & Fuel Cells (01.02.2007)” ve “HFC Czech complementary event (31.01.2007) | 15.08.2006 25.09.2006 4.10.2006 31.01.2007 | 24.08.2006 29.06.2006 6.10. 2006 01.02.2007 | 100 100 100 100 |
| 2 | T.2.1.Purchasing for upgrading of hydrogen production equipment (2005) T.2.2.Purchasing for renewal of hydrogen purification (PSA) equipment (2005) T.2.3.Purchasing for renewal of hydrogen storage equipments (2005) | 01.05.2005 01.10.2005 01.05.2005 | 16.05.2006 13.08.2006 In progress Scheduled Sep.2007 | 100 100 |
| 3 | T.3.3. 16th World Hydrogen Energy Conference (WHEC), 13-16 June2006, Lyon, FRANCE T.3.4. IHEC 2007-Istanbul-TURKEY | 13.06.2006 in progress | 16.06.2006 in progress | 100 |
| 4 | T.4.2. Brokerage Event 2 “Project Marketplace Event on Applied Research and Innovation on Hydrogen Technologies, 15.02.2007, Gebze-Kocaeli-TURKIYE”, 2006/2007 | 15.02.2007 | 15.02.2007 | 100 |
| 5 | T.5.3. Organizing the AB meeting on hydrogen purification technologies, 2006/2007- Gebze/Kocaeli | 16.02.2007 | 16.02.2007 | 100 |
| 6 | T.6.2. Course on Hydrogen purification | 16.05.2007 | 18.05.2007 |  |
| 7 | T.7.2. Technical visit on hydrogen purification technologies, Germany (OWI,FZ GKSS, FZ Juelich, DLR) | 19.02.2007 | 23.02.2007 | 100 |
| 8 | T.8.2. Short Stays on hydrogen rich gas purification | in progress | in progress |  |

3rd period (01.05.2006 – 30.04.2007)

| WP no: | Work performed | Starting date | End date | Contribution to WP, % |
| --- | --- | --- | --- | --- |
| 1 | European Hydrogen and Fuel Cell Technical Review Days 2007”, Brussels BELGIUM. IEA (International Energy Agency) HIA (Hydrogen Implementing Agreement) Task 23 “Small-scale Reformers for On-site Hydrogen Supply (SSR for Hydrogen)” Meeting”,Malmo,SWEDEN EU HfP JTI N.ERGHY (Hydrogen and Fuel Cells Technology Platform Joint Technology Initiative-JTI) N.ERGHY Constitutive General Assembly Meeting”,Brussels BELGIUM | 10.10.2007 30.10.2007 17.03.2008 | 11.10.2007 31.10.2007 17.03.2008 | 100 100 100 |
| 2 | T.2.3. Purchasing for renewal of hydrogen storage equipment | 20.11.2007 | 30.04.2008 | 100 |
| 3 | Task 3.4. of WP3 “Conferences”, “IHEC 2007 International Hydrogen Energy Conference and Exhibition” , Istanbul, TURKEY Task 3.5. of WP3 “Conferences”,“WHTC 2007 World Hydrogen Technologies Convention” on, Montecatini Terme, ITALY Task 3.6. of WP3 “Conferences”, “4thFCEXPO International Hydrogen and Fuel Cell Expo”, Tokyo, Japan | 13.07.2007 4.11.2007 27 .02.2008 | 17.07.2007 7.11.2007 29 .2.2008 | 100 100 100 |
| 4 | Task 4.3. “A Project Marketplace Event on Hydrogen Productio Technologies for Small-scale Applications”, Gebze/Kocaeli, TURKIYE | 03.04.2008 | 04.04.2008 | 100 |
| 5 | Task 5.4. “AB meeting on hydrogen storage technologies” TUBITAK MRC Campus, Gebze-Kocaeli, TURKIYE Task 5.5. “Closing Meeting of the project” | 04.04.2008 04.04.2008 30.04.2008 | 04.04.2008 04.04.2008 30.04.2008 | 100 100 100 |
| 6 | T.6.4. “Course - Hydrogen storage technologies for hydrogen powered vehicles”, Gebze-Kocaeli, TURKEY | 24.03.2008 | 28.03.2008 | 100 |
| 7 | Task 7.3. “Technical visit on hydrogen storage technologies for hydrogen powered vehicles”, Tokyo,JAPAN | 16.04.2008 | 17.04.2008 | 100 |
| 8 | T.8.2. Short Stays on hydrogen rich gas purification T.8.3. Short Stays on hydrogen storage | 20.08.2007 03.09.2007 18.02.2008 25.02.2008 | 07.09.2007 15.09.2007 14.03.2008 21.02.2008 | 100 100 100 100 |

Photos illustrating the work of the project

1st period

WP1

TUBITAK MRC Energy Institute (Center) and some of the project team members

WP2

Hydrogen and fuel cell laboratories

WP3

Task 3.1 IHEC 2005 , Istanbul , 13-15 July 2005   Task 3.2 EHEC 2005, Zaragoza, SPAI

WP4

Task 4.1. 1st Brokerage event – Seminar on hydrogen technologies, 12-13 April 2006

WP5

Task 5.1. Kick-off meeting in 19.September.2005             Task 5.2.Advisory Board Meeting, 14.April.2006

WP6

Task 6.1 “Course on hydrogen fundamentals and hydrogen safety”

WP7

Task 7.1. Technical visit to ENEA and CNR

2nd period

WP2

Hydrogen and fuel cell laboratories infrastructures

WP3

Task 3.3 “16th World Hydrogen Energy Conference,  WHEC 2006” on 13-16 June 2006 in Lyon, France.

WP4

T.4.2. 2nd Brokerage Event “Project Marketplace Event on Applied Research and Innovation on Hydrogen Technologies”, 15.02.2007 in Gebze-Kocaeli-TURKIYE.

WP5

Task 5.3.Advisory Board Meeting-II, 16.February.2006

WP7

Task 7.2. Technical visit to research centers in Germany (19-23 Feb. 2007)

3rd period

WP1

European Hydrogen and Fuel Cell Technical Review Days 2007”, 10-11.October.2007, Brussels BELGIUM.

IEA (International Energy Agency) HIA (Hydrogen Implementing Agreement) Task 23 “Small-scale Reformers for On-site Hydrogen Supply (SSR for Hydrogen)” Meeting”, 30-31.October.2007, Malmo-SWEDEN

“EU HfP JTI N.ERGHY (Hydrogen and Fuel Cells Technology Platform Joint Technology Initiative-JTI) N.ERGHY Constitutive General Assembly Meeting”, 17.March.2008, Brussels BELGIUM.

WP2

WP2   -   Upgraded on-line CO analyzer-MS system to be used hydrogen production studies

WP3

Task 3.4.  “IHEC 2007, International Hydrogen Energy Conference and Exhibition” on 13-17 July 2007, Istanbul, TURKEY.

Task 3.5. of WP3 “Conferences”, “WHTC 2007 , World Hydrogen Technologies Convention” on 4-7 November 2007, Montecatini Terme, ITALY.

4th FC EXPO Registration Hall	             TÜBİTAK MRC Energy Institute Fair Stand

TÜBİTAK MRC Energy Institute Fair Stand

Task 3.6. of WP3 “Conferences”, “4thFCEXPO International Hydrogen and Fuel Cell Expo” on 27th February 2008 and 29th February 2008 in Tokyo, Japan.

WP4

Task 4.3. “A Project Marketplace Event on Hydrogen Production Technologies for Small-scale Applications”, 3-4 April 2008, Gebze-Kocaeli, TURKIYE

WP5

Task 5.4. “AB meeting on hydrogen storage technologies” has been performed in TUBITAK MRC Campus on 4th April 2008, Gebze-Kocaeli, TURKIYE.

Task 5.5. “Closing Meeting of the project”, 4 April 2008 & 30 April 2008

WP6

Task 6.4. Course on hydrogen technologies (Fluent simulation & modeling for hydrogen systems)

WP7

Task 7.3 ENAA (Engineering Advancement Association of Japan) and Senju Hydrogen Refueling Station

Task 7.3 Idemitsu Ichihara Hydrogen Refueling Station

Task 7.3. Technical visit on hydrogen storage technologies for hydrogen powered vehicles (Tokyo, JAPAN)

Project Logo:

Public website:  http://www.mam.gov.tr/hyprostore

2. Dissemination and use

Section 1 - Exploitable knowledge and its Use

NA . Infact this project is a specific support action, there is no concrete research activities defined as knowledge having a potential for industrial or commercial application for developing, creating or marketing a product or process or for creating or providing a service.

Section 2 – Dissemination of knowledge

The objectives of the brokerage events were to discuss hydrogen production, purification and storage technologies, systems and applications. Especially project ideas have been presented and discussed during the event. Participants also presented their institutes, their on-going projects and their opinions about the future projects for the FP7 Programme calls. Introduction of national and international hydrogen fuel cell programs were carried out during these events. In this context, hydrogen knowledge was provided to share mutually and discuss internally. Potential project subjects were discussed mutually and it was resulted some agreement in principle. Hydrogen production and storage were stated as the least developed field in the hydrogen technologies.

Within the brokerage events, conferences and exhibition activities of WPs, lots of contacts have been established with the relevant organizations and individuals from Turkey and European countries (including those from industry, academia and government to enhance the participation in EU FP7 and national project proposals. A well joint networking between the participants was formed during the activities and this will help TUBITAK MRC EI to take part in project proposals in the upcoming future activities of 7th FP.  There were several dissemination activities in different WPs within the project objectives. These are summarized in the following table.

Overview table

Major activities are summarized in the following table.

| Planned/ actual Dates | Type | Type of audience | Countries addressed | Size of audience | Partner responsible /involved |
| --- | --- | --- | --- | --- | --- |
| April 2008 | Project web-site www.mam.gov.tr/hyprostore | General public | EU-World |  | 1 |
| April 2006/ 12-14.04. 2006 | Brokerage event-I | General public Industry R&D Centers | Turkey-EU | ~ 150 | 1 |
| April 2007/ 15-16.02.2007 | Brokerage event-II | General public Industry R&D Centers | Turkey-EU | ~ 200 | 1 |
| April 2008 3-4.04. 2008 | Brokerage event-II | General public Industry R&D Centers | Turkey-EU | ~ 100 | 1 |
| July 2005 13-15.07.2005 November 2005 15-18.11.2005 June 2006 13-16. 06. 2006 July 2007 13-17.07.2007 November 2007 4-7.11.2007 February 2008 27-29.02.2008 | International Hydrogen Energy Congress &Exhibition (IHEC 2005), Istanbul 2nd European Hydrogen Energy Conference (EHEC), Zaragoza, SPAIN 16th World Hydrogen Energy Conference (WHEC), Lyon, FRANCE “IHEC 2007 , International Hydrogen Energy Conference and Exhibition”, 3-17.07.2007,Istanbul, TURKEY “WHTC 2007 , World Hydrogen Technologies Convention” on, Montecatini Terme, ITALY “4thFCEXPO International Hydrogen and Fuel Cell Expo”, Tokyo, Japan | General public Industry R&D Centers | Turkey-EU-World | 3000 | 1 |
| July 2007 February 2008 | Exhibitions- IHEC 2007 – Istanbul FC EXPO 2008-Tokyo | General public Industry R&D Centers | Turkey-EU-World | 3000 | 1 |
| 2005 – 2008 | Posters | General public Industry R&D Centers | Turkey-EU-World | 5000 | 1 |
| 2005 – 2008 | Direct e-mailing | Industry R&D Centers | Turkey-EU-World | 300 | 1 |

Section 3 - Publishable results

NA. This project is a specific support action. There is no consortium. There were no concrete publishable research results for industrial or commercial application etc.

# Text boxes

Hydrogen & Fuel Cell Laboratories

TUBITAK MRC Energy Institute