[image: image1.png]



Project no. 0022745

Project acronym: POORFISH

Project title: Probabilistic assessment, management and advice model for fishery management in the case of poor data availability

Specific targeted research or innovation project

Thematic Priority: PRIORITY 8, Research for Policy Support 

Publishable final activity report
Period covered: from 01/10/2005        to 30/09/2008

Date of preparation: 15/10/08
Start date of project:
01/10/2005        



Duration: 36 months

Project coordinator name: Pierre Failler

Project coordinator organisation name: UoP


Revision [draft, 1]

1. Project execution  

Context and objectives:

The ultimate objective of the project is to create an advisory system (assessment, advice, and/or management) approach based on methods able to deal with data poor systems (utilizing both expert knowledge and published information in addition to existing data sets). Guidelines will be developed for assessment and management of fisheries for sustainability in data poor situations.

There are basically at least three types of data poor situations: 

· Small scale fisheries with usually several target species of otherwise mixed fisheries (many coastal fisheries in Mediterranean and northern Baltic areas)

· Large scale, but recently developed fisheries (many deep sea fisheries belong to this group) 

· Large scale fisheries, where the quality of data is getting worse (poor data due to e.g. misreporting and discarding) 

The project focuses on each of these types, examining a number of case studies within each category. These case studies will have unique characteristics, allowing appropriate tools to be developed and modelled within a diverse range of examples. The approach proposed is a continuation of the work carried out within current EU projects EFIMAS and COMMIT. These projects developed and used a simulation framework to evaluate candidate management strategies before implementation. The framework models both the “real” and observed systems (data collected, assessment and reference points used to guide management) and tests management strategies against plausible hypotheses about the system dynamics. The current project is more focused on management and advice issues, rather than testing of assessment and management combinations within the operational modelling framework. The experiences obtained in the COMMIT salmon case on including stakeholder interview results within the management model will be utilized and further improved here (by methods of KNOWFISH). Moreover, the consortium aims to simplify the somewhat complicated approach used within COMMIT of applying Bayesian assessment approaches. There are also likely to be links between this project and task 4 (risk analysis). Specific questions within the project will be examined with the simulation framework developed under EFIMAS, using it to populate probabilistic advice where necessary and complementing the use of PAMAM. However, it is worth noting that this approach is mainly appropriate where knowledge of species dynamics is reasonable. High degree of uncertainty in parameter estimates will mean that the Bayesian approach is more appropriate in many cases.

The project will also establish some links with the ISTAM project. The two African case studies will be used as a platform to articulate the work done in both project. A more detailed presentation is done in the work plan presentation. 
Contractual partners

	No
	Acronym
	Name and address
	Scientist responsible
	Telephone
	Fax
	Email address

	1
	UOP
	University of Portsmouth 

Winston Churchill Avenue

PO1 2UP, Portsmouth

United Kingdom
	Pierre Failler
	+44 23 92 844 085
	+44 23 92 844 037
	Pierre.failler@port.ac.uk

	2
	IMEDEA
	Institu Mediterrani d’Estudis Avançats (CSIC/UIB)

Miquel Marquès 21, 07190 Esporles, Mallorca, Spain
	Beatriz Morales-Nin
	34-971611721
	34-971611761
	Beatriz.morales@uib.es

	3
	CEFAS
	Centre for Environment, Fisheries and Aquaculture Science

Lowestoft Laboratory

Pakefield Road

Lowestoft

Suffolk

NR33 0HT

UK
	Graham Pilling
	+44 1502 527730
	+44 1502 524569
	graham.pilling@cefas.co.uk

	4
	IRD
	Institut de Recherche pour le Développement

Rue Lafayette

Paris

France
	Raymond Laë
	+33 2 98224511
	+33 2 9822????
	Raymond.Lae@ird.fr

	5
	UHel
	University of Helsinki

Department of Biological and Environmental Sciences 

P.O. Box 65

FI-00014 University of Helsinki
	Sakari Kuikka
	+ 358 50 33 092 33
	+ 358 9 191 58257
	sakari.kuikka@helsinki.fi

	6
	SYKE
	Finnish Environment Institute

P.O.Box 140

FIN-00251 Helsinki

Finland
	Heikki Peltonen
	+358 9 40300236
	+358 9 40300291
	heikki.peltonen@ymparisto.fi

	7
	IFREMER
	Institut Français de Recherche pour l’Exploitation de la Mer

155, rue Jean-Jacques Rousseau

92138 Issy-les-Moulineaux Cedex

France
	Martial Laurans
	+33 2 98 22 43 68
	+33 2 98 22 46 53
	Martial. laurans@ifremer.fr

	8
	AUTH
	Aristotle University

School of Biology

Department of Zoology

Lab. Of Ichthyology

PO BOX 134

54124 Thessaloniki, Greece
	Konstantinos Stergiou
	+302310998268
	+302310998279
	kstergio@bio.auth.gr

	9
	CSIC
	Institut de Ciències del Mar, CSIC

Psg Marítim de la Barceloneta, 37-49

08003-Barcelona (Spain)
	Francesc Maynou
	+34 93 2309500
	+34 93 2309555
	maynouf@icm.csic.es

	10
	IMROP
	Institut Mauritanien de Recherche Océanographique et des Pêches

Po box 22        



Nouadhibou



Mauritanie
	Mamadou Dia
	+:222 245 124
              
	+222 245 081
                
	dvis@toptechnology.mr

	11
	CRODT
	Centre de recherches océanographiques

de Dakar Thiaroye     



PO Box 2241  



Dakar

Senegal

	Moustapha Dème
	221-8340536
	221-8342792              
	mdeme@crodt.isra.sn



Activities
Activity 1: to review the potential assessment and management approaches applied in data poor fisheries. In work package 1, the project will review the potential assessment and management approaches applied in data poor fisheries around the world. It will define the case studies in terms of assessment and management, and obtain expert opinions from actors within the case study fisheries, identifying key problems and issues. 

Activity 2: to develop the basic linkages within the probabilistic assessment and management advice model. In work package 2, the information gained will be used to develop the basic linkages within the probabilistic assessment and management advice model on a case study basis. Current and alternative assessment and management processes will be identified, and utility functions developed, so that performance of alternative approaches can be assessed. 

Activity 3: to apply the probabilistic assessment and management advice model to case studies. Based upon the resulting structure, work package 3 will develop probabilistic data using approaches to develop prior information from literature studies. With this prior information and case study structure, the model will be applied in work package 4 to examine the performance of assessment and management approaches, compared to the current approach used. This will also define the applicability of the model over a wide range of case studies, and identify information of specific value to assessment and management. 

Activity 4: to produce guidelines for assessment and management in poor data situation. Work package 5 will synthesise the cross-case study findings, identifying operational management tools, evaluating the mutual dependencies of management and success, and identify the benefits and failings of the approach across and within case studies. As a result, guidelines will be developed for assessment and management in data poor situations.

Work performed

The work completed in the project consisted mainly of: 1-the review of the potential assessment and management approaches applied in data poor fisheries (WP1); 2-the development of the basic linkages within the probabilistic assessment and management advice model (WP2); 3- the application of the probabilistic assessment and management advice model to case studies (WP3); 4-the application of the probabilistic assessment and management advice model to case studies (WP4) and; 5-the synthesis of the project (WP5). In detais:

WP1 Assimilation

The aims of WP1 were:

· To ensure all partners have a basic understanding of the approaches to be used within the project

· To review the available knowledge base of potential assessment and management approaches applicable to data poor fisheries and compile the information to inform Work Packages 2 and 4

· To review the case study fisheries in terms of current data sources, assessment and management approaches to inform the development of priors under WP 3

· To obtain expert opinions from actors within the case study fisheries on problems and issues to inform Work Packages 2, 3 and 4

Deliverables under WP1 are:

· Manuscript for submission to peer review journals on assessment and management approaches used in data-poor fisheries (global review) (Month 19, April 2007)

· D8 Database of literature on data poor fisheries assessment and management (Month 13, October 2006)

Understanding of approaches

To ensure all project members had an understanding of the approaches to be used within POORFISH, a training workshop was held in Helsinki in May 2006. Training courses on the three proposed software packages were successfully run:

· Bayesian belief networks

· WinBUGS

· FLR

Development of information on the case study fisheries

As part of Work Package 1, Consortium members developed questionnaires to obtain information on their case studies from the variety of fishermen, assessment and management groups involved in the case study fishery. These questionnaires were based upon a basic design developed by the Work Package leaders. Consortium members then used these questionnaires in interviews to identify issues and concerns and new knowledge of interest for the case study design and analysis. These questionnaires have been used in case studies to assist in the development of management questions. 

Manuscript on assessment and management approaches used in data-poor situations

During the reporting period, a review of assessment and management in data poor fisheries was developed to synthesise the information available from the case study fisheries and that gained during the literature review. The outlet selected for this review was the Cefas peer-reviewed book to commemorate 50 years of the seminal publication of Beverton and Holt (1957), who were scientists at the Lowestoft laboratory. This book is now in press and will be published by Blackwell publishing.

The Beverton and Holt chapter examines a number of case studies in detail, to illustrate the problems in assessing and managing fisheries where data is poor. The case studies are:

· Tropical fisheries

· Spanish fisheries 

· Cyclades (Greek) study on Marine Trophic Index

· Deep sea fisheries

· Blue shark 

The reference for the chapter is: G.M. Pilling, P. Apostolaki, P. Failler, C. Floros, P.A. Large, B. Morales-Nin, P. Reglero, K.I. Stergiou, and A.C. Tsikliras. (In press) Assessment and management of data poor fisheries. In Advances in Fisheries Science: 50 years on from Beverton and Holt (Ed. A.I.L. Payne, A.J.R. Cotter and T. Potter). Blackwell Publishing.

D8 Database of literature on data poor fisheries assessment and management.

A database of scientific literature on the assessment and management of fisheries, with particular reference on data poor situations, has been developed in Endnote v6.0.2 (Thompson ISI ResearchSoft). It allows the storing, managing, and searching of bibliographic references within the developed reference library. This software allows references to be directly embedded within Word documents, automatically generating a reference list of those article details inserted. The software allows reference lists to be imported and exported from and two a wide range of alternative reference manager software.

The structure of the database contains a wide range of different details, which vary according to the reference type (paper, book, book section, report etc.). In many cases, the abstract of the paper is also available for viewing, although it should be noted that this is not available in all instances. Currently there are over 250 individual references within the database. This database will continue to be expanded as the project progresses. The database is hosted on the POORFISH website (http://www.poorfish.eu).  

WP2 : Model building 

Objectives of WP2 were to develop stock assessment models suitable for data poor fisheries by constructing case study specific model structures and model codes. Due to the specific features of project case studies, the modelling approach resulted slightly different to that originally anticipated in the technical annex and required active participation from the case study coordinators in the model formulation and analysis. This also meant that a larger contribution than initially foreseen was necessary from UHel, who provided methodological expertise and support. This WP focused in the construction of case study specific model structures and model codes (software).

UHel contributed in the development of case study specific model structures and codes (software) to be used in the case studies no 3, 4, 6, and 7. UHel contributed the following model software to the project in this work package (some of the work was already started in the first reporting period): 

1. Bayesian age-structured fish stock dynamics model including growth, maturity, fecundity, and stock-recruitment dynamics. This model can be easily applied to any temperate pelagic fish stocks, and very little data is required to operate the model. This is a PAMAM model for temperate pelagic fisheries. This model was also used as the basis for the case study 7 model.

2. Bayesian cohort-based model to analyse the Mauritanian Octopus vulgaris fishery (case study 3) including economical aspect.

3. Bayesian state-space population dynamics model to analyse the Senegalese shrimp fisheries (case study 4) including the life history traits of shrimps, hydrologic effects on the recruitment, and migrations of the shrimp population.

4. Bayesian biomass based model for the Cyclades case study (case study 6) which models recruitment separately from aggregated adult biomass.

5.  Bayesian age-structured model for case study 7 (Baltic herring; Finnish Environment Institute has main responsibility). This includes, for example, a novelty work of using Bayesian inference in the analysis of acoustic data.

UHel organised and hosted a workshop in Saaremaa, Estonia in June 2007. The purpose of this workshop was to disseminate modelling knowledge and techniques to deepen the understanding of project members on the methodologies applied within the project case studies. Training on the following two proposed software packages were ran successfully:

-
Bayesian belief networks (Teacher: Laura Uusitalo / UHel)

-
WinBUGS (Teacher: Samu Mäntyniemi / UHel)

The deliverables included in this WP were completed successfully:

-
Deliverable D2: The PAMAM model, written entirely by UHel.

-
Deliverable D6: Manuscript 1 for submission to peer review journals on probabilistic assessment, management and advice model, written mainly by UHel with collaboration from SYKE.
WP3 Development of prior information for case studies

The aims of WP3 were:
· identify data availability for case studies

· gather prior information for case studies

· collect expert information, where necessary

· meta-analysis of data, where necessary

· formulate current assessment, advice or management approach within specific case studies

· identify questions for study within PAMAM

The work under WP3 results in two sets of documents to be delivered to the Commission, Deliverable 3as “Report on case study data identification, collection and validation” and Deliverable 3bs “Case studies data report”.

During the 2nd half of 2006 and the first months of 2007 the work on collating data available to the case studies have progressed satisfactorily. After the methodological meeting in Helsinki (May 2006) partners have been able to approach the subject of prior computation. Given the nature of the problem in a context of poor data availability, the computation of priors has not been easy. As reported for WP1, the task has been aided by interviews with stakeholders and experts. The following table presents the methodological approach used for each case study. 

Table 1: Methodological approach used for each case study
	Case study
	Methodological approach
	Leading (Co-operating) institutes 
	Additional data req.

	Case study 1

Blue ling
	FLR, (economic analysis)
	Cefas (IFREMER, UoP)
	French catch data, deep sea spp. price data from France (OFIMER), Faeroes. SRR

	Case study 2

Edible crab
	FLR (BAYESNETS, BAYES and economic analysis)
	Cefas,

(IFREMER, UoP)
	French price data, French catch and effort, lfreq?

	Case study 3

Cephalopods
	BAYES and economic analysis in parallel
	IMROP (UHel, UoP)
	International prices: Japan, Spain, Italy (see FAO). Landing and export prices time series from Maur. UHel to focus questions for RIVOT scientist

	Case study 4

Shrimps
	BAYESNETS, BAYES
	CRODT (IRD, UHel)
	Expert knowledge through future workshop

	Case study 5a

Artisanal Barcelona 
	FLR (WinBugs/BAYESNET, economic analysis)
	CSIC (IMEDEA, Cefas)
	

	Case study 5b

Artisanal Majorca
	FLR (WinBugs/BAYESNET, economic analysis) 
	CSIC/IMEDEA (Cefas)
	Sampling to be completed

	Case study 6

Cyclades


	FLR, simple multispecies simulation models
	AUTH (UoP(FL), Cefas/UHel)
	

	Case study 7

Baltic Herring


	BAYES
	SYKE (UHel)
	Fisher logbook information for priors. Selectivity information?

	Case study 8 Saronikos Gulf
	FLR (BAYES, economic analysis)
	UoP (FL) (Cefas) 
	Further information to be gathered


Deliverable D3as, following a template suggested by the workpackage leader (CSIC), has been finalized in October 2007. D3bs have been finalized timely in November 2007. Both are are presently available in a published format on the Poorfish portal (www.poorfish.eu).
WP4 Application of the model to case studies

The initial objectives of this WP as reported on the technical annex were the following: 

· Apply the model to case studies to examine specific questions hypothesized in WP2

· Assess the model applicability

· Examine value of information for assessment and management 

· To create assessment, management and advice models that take into account high uncertainty in data poor assessments 

· To test the models with real and simulated data sets

However, during the development of the project and specifically of WP2, these had to be changed. At Syros meeting on 2006, it was noted that the modelling approach undertaken in the project was slightly different to that originally anticipated in the project technical annex. It was agreed that, based upon the experiences of the first year of the project, the generic approach suggested within the technical annex would not result in meaningful outputs for management evaluation. The cases studies seem to have so specific features, that one generic model cannot be applied. Both the type of life cycles and the management tools applied lead to the need of case specific models. This means also that case study coordinators must actively participate to the model formulation and then carry out the analysis. The opinion was that the case studies fell under three general areas: 

1. Northern European fisheries with TAC management and age-related data (e.g.

Baltic herring)

2. ‘Mediterranean’ fisheries with CPUE and in some cases length data, covering both effort and technical measure controls (e.g. Spanish and Greek case studies, edible crab) and TAC and technical measure controls (e.g. deep water case study) 

3. ‘African’ fisheries with environmentally driven, short lived species where management was aiming to maximize fishing opportunities while sustaining stocks Generic guidelines were anticipated from a synthesis across the case studies as a whole and within these three groups, while there seems to be some generic features inside of the groups above. However, it must be noted that a generic model is no longer anticipated to cope with the specifics across each of the range of case studies.

After completion of WP3 and in the Thessaloniki meeting on 2008, it was agreed to include in the WP deliverables a series of considerations on the selected models, their applicability, the quality of the results and its associated uncertainty, the management applicability and the identified gaps to be solved in future developments. 

Within this work package, the specific models developed in WP3 are populated and applied to examine the selected range of plausible assessment and management approaches for the case studies. Thus enabling the demonstration of subjective choices of scientists and/or managers and making it easier to decide which parts of the knowledge should be improved by new studies. This will focus future data collection programmes. 
The developments in the model implementation by each case study in WP4 in relation to WP3 are described below: 
	Case study
	Model applied WP3
	Development WP4

	Blue ling deep water fishery (North Atlantic, Europe)
	Effort distribution
	Closed areas effects on fishing effort distribution

	Edible crab (English Channel, Europe)
	Schaeffer fitted with Bayesian estimation and FLR length area structured simulation model
	Schaefer fitted with Bayesian estimation and FLR length area structured simulation model

	Cephalopod fishery (Mauritania, West Africa)
	Bio economic analysis of the Mauritanian cephalopod fishery
	Age-structured intra-annual Bayesian population dynamics model based on biological parameters adopted from literature. This probabilistic stock assessment model is implemented with economic information – relative value of commercial size groups

	Shrimp fishery (Senegal, West Africa)
	Cohort model with Bayesian approximation
	Impact of environmental variations (upwelling and freshwater inputs) and fishing effort on the sequential shrimp fisheries

	Barcelona/Majorca artisanal fishery (Spain, Mediterranean Sea)
	Barcelona recompilation of data, Majorca Schaeffer production, Bayesian unsuccessful
	Barcelona Schaeffer fitted with Bayesian approximation

Majorca bio-economic model using MEFISTO



	Cyclades fishery (Greece, Mediterranean Sea)
	MTI

Bayesian single stock study
	MTI with improved catch estimates 

Bayesian single stock study

	Baltic herring (Baltic Sea, Europe)
	Probabilistic age-structured model of Baltic Sea herring
	The probabilistic age-structured stock assessment model is tuned with probabilistic hydro acoustic data. Besides, .g. the predation mortality estimates are included.

	Saronikos Gulf Beach Seine fishery (Greece, Mediterranean Sea)
	Fox&Schaeffer&Pella Tomlinson models
	FLR bio-economic model


Report D4, deliverable of the WP4 included D4-1 to 8, reporting the case studies results and D4-9 to D4-16 including the publications resulting from the studies undertaken. Some of them are already published on SCI Journals whilst others are still in the draft level. 

WP5 Synthesis

The aims of WP5 were:

· Disseminate the project model principles to key fishery stakeholders

· Identify operational management tools (data collection, assessment and management approaches) for data poor situations

· Identify benefits and failings of the modelling approach both across case studies and on a case study specific basis.

· Develop guidelines for assessment and management in data poor situations
The international workshop entitled: “Data poor modelling towards ecosystem fisheries management” was held in the University of the Balearic Islands, Majorca Island, Spain, 8-9 September 2008. The workshop was attended by more than 40 people from Europe, Africa and North America. A workshop report has been produced and available on the portal as D5a. 

A synthesis of assessment and management processes in data poor fisheries has been undertaken with the collaboration of the majority of the POORFISH partners. The results of the case studies performed in work package 4 and a review of other methods have been used to identify which characteristics of data poor fisheries are keys in determining the approaches that can be undertaken, and what information is best gathered to improve knowledge and effectiveness of assessment/management by new studies. An examination of the benefits and failings of the main approaches developed in the project has been made with the identification of where improvements should take place. Main results are part of the D5b report.  

Guidelines for fishery advice in poor data situations have been developed. The consortium identified which elements of the project should be applied in cases where data are assumed to be of better quality. This framework helps to define the most appropriate routes to formulate scientific advice for successful management of data poor fisheries. Results are part of the D5b report and the D18 paper submitted to Fishery Research in November 2008.

Project Logo: 

Project webpage: www.poorfish.eu

Annex 1 – Plan for using and disseminating the knowledge

Section 1

Not applicable as there are no results that have potential for industrial or commercial application.

Section 2

The section below gives information on the two reporting period activities. The indication (Date) in brackets in the Column “Planned/actual dates” corresponds to the initial date as indicated in the TA. It is follows by the actual month and year of delivery.

Overview table 

	Planned/actual

Dates 
	Del. No.
	Type


	Type of audience
	Countries addressed
	Size of audience
	Partner responsible /involved

	
	
	Press release(press/radio/TV)
	
	
	
	

	August 2008
	Not a del. 
	R. Synge, P.Failler and D. Gascuel (2008), Over-exploitation in West Africa’s richest zones, African report, no. 12, Aug-Sept issue, p. 28
	Policy makers
	All
	Aug.  2008
	UoP 

	
	
	
	
	
	
	

	

	
	
	Media briefing
	
	
	
	

	
	
	None
	
	
	
	

	

	
	
	Conferences and international workshops
	
	
	
	

	5-8 Dec.  2005
	None
	Governance of West African fisheries, PRCM annual forum, Banjul, Gambia, 
	Research and public policy makers
	West Africa Sub-region 
	250
	UoP

	13-15 February 2006 
	None
	ISTAM meeting 
	Research
	West Africa and Europe
	50
	UoP

	22-23 March 2006
	None
	Second scientific committee of the Caribbean Regional Fishery Mechanism
	Research and public policy makers
	Caribbean
	500
	UoP

	27-30 June 2006
	None
	Second workshop on methods of the Caribbean Regional Fishery Mechanism
	Research
	Caribbean
	25
	UoP

	3-4 July 2006
	None
	UK Defra R&D project discussion
	Research and fisheries managers
	UK
	30
	Cefas

	1-12 May 2006
	None
	ICES WGDEEP assessment working group
	Research
	Europe
	20
	Cefas

	17-21 Sept 2007
	None
	Kirsi-Maaria Järvenpää et al. (2007), Bioeconomic analysis of the Mauritanian 
cephalopods fishery, ICES CM 2007
	Research and public policy makers
	World
	400
	UHEL

	17-21 Sept 2007
	None
	P. Failler and al. (2007), Probabilistic assessment, management and advice model for fishery management in the case of poor data availability, ICES Conference, Session O
	Research and public policy makers
	World
	400
	UoP

	26-28 Nov.  2007
	None
	G. Pilling (2007), presentation of the POORFISH project at "The Bare-foot Ecologist Toolbox workshop", Vigo.
	Research and public policy makers
	European
	150
	UoP

	19 June 2008
	None
	P. Failler (2008), the POORFISH project, presentation at the Caribbean Fisheries Regional Mechanism 4th Annual Science Meeting, St. Vincent and the Grenadines
	Research and public policy makers
	Caribbean
	400
	UoP

	19 June 2008
	None
	G. Piling (2008), The FLR method, presentation at the Caribbean Fisheries Regional Mechanism 4th Annual Science Meeting, St. Vincent and the Grenadines
	Research and public policy makers
	Caribbean
	400
	CEFAS

	21-26 July 2008
	None
	P. Failler et al. (2008), Probabilistic assessment, management and advice model for fishery management in the case of poor data availability, IIFET conference, Vietnam
	Research and public policy makers
	World
	600
	UoP

	
	
	
	
	
	
	

	

	
	
	Exhibition
	
	
	
	

	
	
	None
	
	
	
	

	

	
	
	Reports
	
	
	
	

	(Jul. 06)

Aug. 06
	D1
	Report on Probabilistic assessment, management and advice model 
	Research and public policy makers
	All
	NA
	CEFAS

	(Sep. 07)

Sep. 07
	D2
	PAMAM model
	Research and public policy makers
	All
	NA
	UHEL

	(Jan. 07)

Oct. 07


	D3as
	Report on Case study data identification, collection and validation (Case studies progress report)
	Research and public policy makers
	All
	NA
	CSIC

	(Sep. 07)

Nov. 07
	D3bs
	Case studies data report
	Research and public policy makers
	All
	NA
	CSIC

	(Dec. 07)

Dec. 07
	D4s
	PAMAM application to case studies 
	Research and public policy makers
	All
	NA
	IMEDEA

	(May 08)

May 08
	D4
	Report on Practical operational management tool (case studies model application)
	Research and public policy makers
	All
	NA
	IMEDEA

	(Sep. 08)

Oct. 08
	D5a
	Report on dissemination workshop
	Research and public policy makers
	All
	NA
	UoP

	(Sep. 08)

Oct. 08
	D5b
	Report on management processes in data poor fisheries
	Research and public policy makers
	All
	NA
	UoP

	

	
	
	Journal papers
	
	
	
	

	
	
	
	
	
	
	

	(Dec. 2006)

Dec. 2006
	D6
	Manuscript 1

Uusitalo, L., Mäntyniemi, S., Peltonen, H., Pönni, J., and Kuikka, S. A probability model to estimate pelagic fish stock dynamics and biological reference points: the Bothnian Sea herring as an example. Manuscript to be submitted to ICES journal of Marine Science
	Research
	Worldwide
	NA
	UHeL/

SYKE

	(Apr. 07)

June 08
	D7
	Manuscript 2

Merino G., B. Morales, F. Maynou, A. Maria Grau, The Majorcan trammel net fishery: status and perspectives, Submitted to Aquatic Living Resources
	Research
	Worldwide
	NA
	IMEDEA leader

	(May 08)

Dec. 08
	D9
	Manuscript 3

Large P. A., Guzman Diez, Martial Laurans, Graham M. Pilling, David Reid, Jacup Reinert, Andrew B. South and Vladimir I. Vinnichenko.
The spatial and temporal distribution of spawning aggregations of blue ling (Molva dypterygia) to the west and north-west of the British Isles (ICES Areas Vb, VI, VII and XIIb), submitted to ICES journal
	Research
	Worldwide
	NA
	CEFAS leader

	(May 08)

Sep. 08


	D10
	Manuscript 4

Laurans M, and M.T. Smith, Bayesian production model assessment of edible crab in the English Channel
	Research
	Worldwide
	NA
	IFREMER leader

	(May 08)

Sep. 08
	D11
	Manuscript 5

Janvenpaa K et al., Bioeconomic analysis of the Mauritanian Cephalopods fishery
	Research
	Worldwide
	NA
	UHeL

	(May 08)


	D12
	Manuscript 6

Laë R., Anttii-Poika V.P., Järvenpää K.M., Grüss A., Mäntyniemi S.,

Juntunen T., Uusitalo L., Deme M., Diadhiou H., Kuikka S., Bayesian shrimp (penaeus notialis) population dynamics state-space modelling:

application for Casamance estuary (Senegal, West Africa).
	Research
	Worldwide
	NA
	IRD leader

	(May 08)

Aug. 08
	D13
	Manuscript 7

Maynou F. Analysis of catch and effort time series of the Barcelona artisanal fishery

through Bayesian surplus production models
	Research
	Worldwide
	NA
	CSIC 

	(May 08)

Aug. 08
	D14
	Manuscript 8

Juntunen T., A. C. Tsikliras,

S. Mäntyniemi, K.  Stergiou, A Bayesian population model to estimate changes in the stock size under poor data availability using Mediterranean bogue (Boops boops) and picarel

(Spicara smaris) as an example
	Research
	Worldwide
	NA
	UHeL/ leader

	(May 08)

Oct. 08
	D15
	Manuscript 9

Peltonen H., S. Mäntyniemi, L. Uusitalo  and S. Kuikka, Probabilistic Baltic Sea herring (Clupea harengus L.) stock assessment
	Research
	Worldwide
	NA
	UHeL leader

	(May 08)

Sep. 08


	D16
	Manuscript 10

Pilling G.,  F. Scott, C. Karlou-Riga and I. Anastopoulou, The implications of technical management measures for stocks and fleets in the Saronikos Gulf, Greece
	Research
	Worldwide
	NA
	CEFAS leader

	(Jun 08)

Sep. 07


	D17
	Manuscript 11

Reglero P. And B. Morales-Nin, Relationship between first sae price, body size and total catch of trammelnet target species in Majorca, Fisheries Research 92 (2008), pp. 102-106.
	Research
	Worldwide
	NA
	IMEDEA leader

	(Sep 08)


	D18
	Manuscript 12

Stergiou K, Pierre Failler, Graham M. Pilling, Sakari Kuikka, Francesc Maynou, Beatriz Morales-Ninf, Rainer Froese, Protolean fisheries, models and management: simple approaches to complex problems, under revision, Fishery Research. 
	Research
	Worldwide
	NA
	AUTH leader

	

	
	
	Book Chapters
	
	
	
	

	Aug. 07
	Not planned
	Manuscript 2

Pilling, G.M., Apostolaki, P., Failler, P., Floros, C., Large, P.A., Morales-Nin, B., Reglero, P., Stergiou, K.I., and Tsikliras, A.C. 2008. Assessment and management of data-poor fisheries. In Advances in Fisheries Science. 50 years on from Beverton and Holt, pp. 280-305. Blackwell Publishing, Oxford. xxi + 547 pp.
	Research
	ICES and worldwide
	NA
	Cefas and other partners

	Dec. 08
	Not planned
	B. Masumbuko, M. Ba, P. Morand, P.Chavance, P. Failler (2008), Stakeholders’ perceptions on scientific advices for fisheries management in West Africa; Can scientific advices help to cope with global change in marine social-ecological systems? in Ian Perry, Philippe Cury, Dawn Ashby and Rosemary Ommer, Blackwell's FAR series. Chapter submitted and under review


	Research and public policy makers
	All
	NA
	IRD/

UoP



	
	
	
	
	
	
	

	

	
	
	Project web-site
	
	
	
	

	January 2006
	
	Poorfish Portal  
	Research, public policy makers, Higher education
	all
	
	UoP/UHEL/CEFAS

	

	
	
	Posters
	
	
	
	

	

	
	
	Flyers
	
	
	
	

	(Nov 06) 
April 07
	LEA1
	Leaflet of POORFISH presentation for wide distribution. Produced in English, Finnish, Greek, Spanish, Catalan, Arabic, Wolof and French
	General public
	All
	NA
	All partners in their mother tong language

	Nov. 07

Apr 08
	LEA2
	Leaflet of presentation of the international worksho, Majorca, 8-9 September 2008 
	Research, public policy makers, Higher education
	All
	NA
	UoP

	Sep 08
Oct 08
	LEA3
	Leaflet of presentation of the main findings of the POORFISH project
	Research, public policy makers, Higher education
	All
	NA
	UoP

	

	
	
	Electronic databases
	
	
	
	

	(Oct. 06)

Dec. 06
	D8
	Electronic database of literature on data poor fisheries
	Research
	All
	NA
	CEFAS

	

	
	
	Direct e-mailing
	
	
	
	

	
	
	Not planned at the moment
	
	
	
	

	

	
	
	Film/video
	
	
	
	

	
	
	Not planned at the moment
	
	
	
	

	
	
	
	
	
	
	

	
	
	
	
	
	
	


Section 3

Not applicable
� EMBED  ���





� EMBED  ���








4

_-1316350392.unknown

_1249977082.unknown

