Milestones

| Table 2. Milestones |  |
| --- | --- |
| Milestone no. | Milestone name | Work package no | Lead beneficiary | Delivery date from Annex I | Achieved Yes/No | Actual / Forecast achievement date | Comments |
| MS 1.1 | Activity plan: Common research training plan (updated every year), schedule for common visits | WP1 |  | M2, 13 |  | M2, M13 | Achieved. Activity Plan Reported |
| MS 2.1 | Selection and evaluation criteria | WP2 |  | M3 |  | M3 | Achieved. Evaluation Reported |
| MS 2.2 | Evaluation and grant extension decision for the appointed researchers | WP2 |  | Every 12 months |  | M12 | Achieved. Researchers Appointed |
| MS 3.1 | Final list of new equipment for procurement, final estimation of total costs, final specifications, and public call to tender on the website | WP3 |  | M6 |  | M6 | Achieved. Public Procurement Notice Published |
| MS 3.2 | Evaluation of offers and purchase of equipment | WP3 |  | M12 |  | M8 | Achieved. Evaluation Reported and Purchase Order Placed |
| MS 3.3 | Installation and testing of equipment | WP3 | M24 | Reporting of Equipment Installed |  | M24 | Achieved. Reported |
| MS 4.1 | Establishment of the date, topics and invited speaker list for the future application workshops | WP4 |  | M15 |  | M15 | Achieved. Workshop Agenda Publicly Published |
| MS 4.2. | Creation of the working group for preparing the strategic workshop | WP4 |  | M12 |  | M12 | Achieved. Members of the Working Group are Reported |
| MS 4.3 | Strategic Workshop | WP4 |  | M18 |  | M18 | Achieved. Workshop Minutes Reported. Conclusions of the workshop. |
| MS 5.1 | NANOMAT Website | WP5 |  | M4 |  | M3 | Achieved. Website Publicly Published |
| MS 5.2 | Market Research Survey | WP5 |  | M18 |  | M18 | Achieved. Market Research Reported |
| MS 5.3 | Nanomaterials book | WP5 | M24 | Published Publicly |  | M33 | The delivery date was postponed by Steering Committee decision to fully represent the research made during the project. Achieved. Published |
| MS 6.1 | First reporting period report | WP6 |  | M18 |  | M18 | Achieved. Report Issued |
| MS 6.2 | Project review meeting involving Project Officer and Evaluation Team | WP6 |  | M18 |  | M18 | Achieved. Project officer did not participate. Review Meeting Minutes Reported |
| MS 6.3 | Project completion | WP6 | M36 | Final |  |  | Project completed. |
| MS 6.4 | Final meeting involving Project Officer and Evaluation Team | WP6 | M36 | Final Meeting Minutes Reported | MS 6.4 | Final meeting involving Project Officer and Evaluation Team | Final meeting took place in Barselona, March 2, 2012. Minutes reported. |