Project number: INCO-CT-2006-026426

Project acronym: SOLARBUILD

# Project title:  Integration of solar technologies into buildings in Mediterranean countries

Instrument: Specific support action

Thematic Priority:

# PERIODIC MANAGEMENT REPORT

Period covered: from 1/1/2007    	to 29/2/2008

Date of preparation: 3/2008

Start date of project:		1/1/2007				Duration:  14     months

Project coordinator name: Dimitris Papastefanakis-Kiki Papadopoulou	Version: 1st

Project coordinator organisation name: Centre for Renewable Energy Sources

ACTIVITY REPORT

- WP1: Project coordination

Firstly, all the necessary contacts with the Commission for the formation of the final technical and financial annexes of the contract have been made. This action took a very long time and great effort. To the last changes, we had to add the withdrawal of the Egyptian energy centre from the consortium due to their internal reasons. The work and the respective budget of OEP have been undertaken by the coordinator.

The pre-financing has been transferred to the partners after the reception from the Commission. This also took long time for some organisations as the details concerning their bank accounts reached CRES late.

A project organisation committee from CRES, MEDENER and UMAR representatives was formulated for the better communication between all and especially UMAR members in the participating countries which are not project partners. The kick off meeting was realised at CRES premises in Athens, on 9 February 2007 (please find minutes attached). The participating organisations (CRES & NERC) took the responsibility to inform the rest partners (MEDENER members) to the forthcoming MEDENER meeting in Rome. In parallel UMAR members were informed by their General Secretary in their association meeting.

During the kick off meeting, the detailed implementation plan as well as the time schedule for each activity was presented.

The second project meeting has taken place in Athens in parallel to the 2nd project workshop on 12-13 December, mainly between UMAR and CRES, and contained the definition of the last details for the data collection for the reporting and elaboration of the E-guide.

CRES has continuous communication with the partners for administrative and technical issues. It especially contacted and stressed the deadlines for the reports to the Commission.

During this last two months, CRES has started preparing the period management report for the first period 1/1/2007-31/12/2007. As coordinator, it has forwarded all the necessary information for the preparation of the report to the partners as well as the relative messages received by the EC officer. The deadline for the submission for this document was 15 February 2008, but despite the Commission officer’s reminders and the continuous e-mails and telephone calls of the coordinator to the partners, the report submitted was incomplete.

Only a few members responded to the first deadline, and then the coordinator started a long procedure of asking/reminding about the documents and updating the interim report. There were continuous contacts with the Commission financial officer, informing about the situation and asking for guidelines.

At the end of this period, the Coordinator has started preparing the next/final report for the period 1/1/2008-29/02/208. The same procedure with the same difficulties has started for the collection of the necessary documents. CRES technical and financial departments have been dealing with the reports from January 2008 until 26/5/2008 which is the last deadline given by the Commission.

- WP2: Expert working groups

This work package included the establishment of working groups in each country comprising mainly the energy agency-MEDENER member in each country and the relevant architects associations. Other relevant professions were motivated to participate. It could be said that this was a very difficult task, as finally was proven that in most of the countries, there is no cooperation between energy centres and so relevant associations such as the architects one.

CRES along with UMAR have made great effort (correspondence, telephone calls, meetings with any chance) to bring together the national key actors.

In most of the cases, it was finally achieved to have at least one meeting between the energy centre and the respective UMAR member and then to have telephone or e-mail contacts for the market analysis needs and also the representation to the workshops.

- WP3: Market analysis

The guidelines have been prepared for the market analysis report and have been distributed to every partner (guidelines attached, annex II). The input that has been received varied a lot depending on the situation in each country and the available data. CRES has come back in many cases asking for more info or clarifications so as to finalise the documents and prepare then the E-guide.

- WP4: Workshop in Morocco

According to the work programme, the first workshop has been realised in Marrakech, Morocco, on 25 of October 2007. The event announcement has been prepared and mailed to the target group, as well as other promotional material which has been distributed during the workshop (folder, presentations, etc). The workshop has been attended by about 50 persons (list of participants, programme and other promotional material attached).

- WP5: Workshop in Greece

The next workshop has been organised in Athens, Greece, on 12-13 December 2007 by UMAR (local representative) and CRES. The event has been taken place at the National Research centre and was attended by more than 150 people. The Vice Minister for Development has welcomed the participants as well as the General Secretary of UMAR and the president of CRES. The event was followed by live discussion which focused on topics like the integration of RES in public buildings, architects training, future collaboration, etc.

In this second project event, the rest participating countries, Jordan, Palestine, Greece, Spain and Lebanon presented their market studies. Besides, an overview of the market studies presented in Morocco closed the session.

An exposition of Architecture Students work entitled “The conception of a dense habitat of positive energy adapted to the Mediterranean climate” took place during these two days of the workshop.

The promotional material included the event announcement, final programme, conference bags, posters, CD with summaries of the market studies and project overview. Translation and catering has been undertaken by UMAR. Besides, press releases have been sent to technical magazines, to newspapers in Greece and have been also put on the partner’s sites and of course the project site.

The presentations are available on the project site.

- WP6: Electronic guide and Web

a. Following the organisation of the two workshops, based on the presentations given during them and the market studies elaborated in WP3, CRES has prepared the E-Guide. The guide include the situation in each country, relevant trends, development in Europe, good practices, tackling hurdles and recommendations-next steps. Where there was not enough input from local resources, CRES has searched info through the internet or results of other European projects.

The E-guide has been to partners for their comments and next to the project officer. Following the project officer’s suggestion the guide along with a brief project description will be sent to the CORDIS database for greater dissemination.

b. A site has been developed for project dissemination needs. The address is www.cres.gr/solarbuild

All public documents produced during the project implementation are on the site: the workshop announcements, relative press releases, the event presentations, general project description, the partners, and of course the E-guide.

- WP7: Follow-up – General Dissemination Activities

A list of follow up activities will be drawn up in order to maintain a permanent dialogue between MEDENER and UMAR members. Besides, main results such as the E-guide will be disseminated through the project web and the web sites of each partner. Finally, press releases and articles to newspapers are planned in order to disseminate project results.

DEVIATIONS

The main issue that could be referred is the difficulty to the contacts between the members of the consortium (not all of them). It is supposed that it is due to the very low budget of the partners, the difficulty in getting input during the implementation of the project as well as during the reporting period. This was resulted to the submission of an incomplete interim report and greater efforts of some partners in contacts and in searching info from other sources to prepare the project deliverables.

Extra effort has been put for the preparation and completion of the interim and final report according Commission’s instructions in order to meet the new deadline on 26 May 2008.