Final Activity Report

SSA 28449

[image: image1.png]



Project no. 028449

Project acronym: Tripl-E DOSE
Project title: Days of Socio-Economy: Education, Employment, Europe
Instrument: SPECIFIC SUPPORT ACTION
Thematic Priority PRIORITY 7: CITIZENS AND GOVERNANCE IN A KNOWLEDGE-BASED SOCIETY

Publishable Final Activity Report 
Period covered: 01.02.2006 to 31.07.2007


Date of preparation: August 2007
Start date of project:
01.02.2006



Duration: 18 months
Project coordinator name: Wiesław Studencki
Project coordinator organisation name: Institute of Fundamental Technological Research, Polish Academy of Sciences (IFTR)

Revision [draft, 1, 2, …]
Project execution


Project title: Days of Socio-Economy: Education, Employment, Europe
Project acronym: Tripl-E DOSE
Project public website: http://www.kpk.gov.pl/triple/ 
The project was prepared as a response to the Call for Proposals FP6-2004-CITIZENS-6, subject - 8.3.2. New approaches for policy-research dialogues in the ERA: targeted dissemination of EU research in national and multi-national contexts.

Two institutions participated in the project:

1. Institute of Fundamental Technological Research, Polish Academy of Sciences (hosting the National Contact Point), Warsaw - Coordinator (Wiesław Studencki);
2. Jagiellonian University, Cracow (Jolanta Perek-Białas, Marek Frankowicz); 

with great assistance of the Warsaw School of Economics.

The main idea of the project was to summarize and disseminate outcomes of socio-economic research resulting from the FP5 and FP6 projects which were related to the spheres of education and employment in Europe. For this purpose, the conference Education, Employment, Europe was organised on 21-22 September 2006 in Cracow. 
The direct objective of the conference was to transfer the applicable, practical knowledge produced under two clusters of EU-funded projects (i.e. concerning education and employment) towards target groups involved in the implementation of respective policies at different levels, to receive their feedback, to elaborate recommendations for the future and to enhance mutual links and co-operation.
Several keynote speakers were invited and contributed to the conference: 
1. Virginia Vittorino (European Commission, DG Research)

2. Constantinos Fotakis (European Commission, DG Employment, Social Affairs and Equal Opportunities)
3. Jerzy Buzek (European Parliament)
4. Louise Morley (University of Sussex, United Kingdom)
5. Vaiva Zuzeviciute (Vytautas Magnus University, Lithuania)

6. Margarita Tereseviciene (Vytautas Magnus University, Lithuania)
7. Frieda Bergman (South Sweden European Office, Belgium), Liselotte Rooke (Region Skåne, South Sweden)
8. Don F. Westerheijden (University of Twente, the Netherlands)
The conference included two types of events:

· plenary sessions consisting of “Voice of Science”: keynote speakers - researchers - presented general introduction to stimulate participants for further discussion during workshops; “Voice of Practice”: speakers - practitioners - presented their views about research in relevant fields;
· workshops: 1) to receive feedback from the non-research audience: critical assessment of researchers work as well as expectations and ideas of new research tasks to be undertaken in future FP7 projects; 2) to formulate recommendations towards policymakers at different levels.

Nine workshops were organised:

· Active ageing in the labour market and education 

· Persons with disabilities in education and on the labour market

· Quality vs. inequality in education and on the labour market

· Education for a civil society

· Life–long learning and employment

· Foreign workers (EU and non-EU) in the local labour markets

· Inheriting social inequalities within education and the labour market 

· Family-friendly work arrangements

· Intergenerational learning and employment

Workshop flyers have been prepared for the participants, including short information on the subject, questions to workshop leaders and list of relevant FP projects involved.

Poster session was attended by 60 participants and the presentations triggered new ideas of cooperation.
108 participants registered to the conference, 105 (including 13 last minute registrations) attended (24 from AT, CZ, DE, EE, ES, IE, IT, IS, LT, NL, PT, SK, UK).
The contributions presented during the conference and summaries of workshops (including recommendations) have been made available at the project website.
Follow-up seminar Framework Programmes and European Social Fund for Education and Employment in Europe was organised to discuss FP 7 SSH research topics versus expectations and needs of the education and employment sectors as well as links of Cracow conference recommendations offered to both sectors by structural funds. Two panel discussions formed the core of the seminar:
1. Socio-economic research under Framework Programmes and its value for policy making.

2. Education and Employment: benefits from ESF

Several specialists were invited and participated in the panels. In the Panel 1:

· Ronald Schoenmaeckers (Population and Family Study Centre, Belgium)
· Jean-Louis Meyer (University of Nancy, France)

· Wielisława Warzywoda-Kruszyńska (University of Lodz, Poland)

· Irena E. Kotowska. (Warsaw School of Economics, Poland)

In the Panel 2:

· Jarosław Górniak (Jagiellonian University, Cracow, Poland)

· Petri Uusikylä (NET EFFECT, Helsinki, Finland)

· Sandro Turcio (IPPS – CNR, Penta di Fisciano Salerno, Italy)
· Krzysztof Musiatowicz (Regional Labour Office, Szczecin, Poland)
· Maciej Szałaj (Polish Agency for Enterprise Development)
77 participants registered to the seminar, 45 attended (from CZ, FI, FR, IT, PL).
The presentations shown during the seminar are available at the project webpage http://www.kpk.gov.pl/triple/s_presentations.html  .
Two volumes of the Conference Proceeding - English and Polish language versions - have been published (2500 and 2000 copies, respectively) and distributed among conference and seminar participants as well as sent to potentially interested institutions: the European Commission, National Contact Points, Polish ministries relevant to spheres of science, education, employment, economic development, regional development, Polish Regional Labour Offices, regional authorities, universities and research institutes in Poland and abroad.

The work has started on the project information system SPIRIT - Socio-economic Project Information on Research, Information and Teaching - which evolved from the Tripl-E DOSE idea of simple repository of socio-economic projects. The system  is being built at the Jagiellonian University to encompass exhaustive data on projects financed by different programs. 
Dissemination and use

The dissemination of EU research in national and multi-national contexts was inherent activity of the project, as defined by the Call for Proposals FP6-2004-CITIZENS-6. 
Overview table 
	Planned/actual

Dates 
	Type


	Type of audience
	Countries addressed
	Size of audience
	Partner responsible /involved

	10/8
	Conference
Education, Employment, Europe
	Researchers, Ministry officials, Labour offices
	EU/Associated
	105
	2

	16/17
	Seminar Framework Programmes and European Social Fund for Education and Employment in Europe
	Researchers, Ministry officials, Labour offices
	EU/Associated
	45
	1,2

	16/17
	Publication Conference proceedings in English
	Researchers, Ministry officials, Labour offices
	EU/Associated
	2500
	1,2

	16/18
	Publication Conference proceedings in Polish
	Researchers, Ministry officials, Labour offices
	EU/Associated
	2000
	1,2


	1/2
	Project web-site
	all
	all
	
	1

	2006-7
	Direct e-mailing
	research
	AT, CZ, DE, EE, ES, IE, IT, IS, LT, NL, PT, SK, UK
	
	1-2

	16/17
	Film/video
	research
	PL
	
	2

	17
	photographic documentation
	research
	all
	
	1


The conference Education, Employment, Europe was the core disseminative project activity. Its objective was to transfer the applicable, practical knowledge concerning education and employment towards target groups involved in the implementation of respective policies at different levels. It consisted of “Voice of Science” and “Voice of Practice” plenary sessions complemented with 9 workshops. The conference gathered 108 specialists from 13 countries.

Additionally, the follow-up seminar Framework Programmes and European Social Fund for Education and Employment in Europe was organised to discuss FP 7 SSH research topics versus expectations and needs of the education and employment sectors as well as links of the conference recommendations offered to both sectors by structural funds. The seminar attracted 45 participants from 5 countries. The presentations are available at 

http://www.kpk.gov.pl/triple/s_presentations.html  .

Conference proceedings in two language versions were published, 2500 copies in English, 2000 in Polish and distributed among conference and seminar participants as well as sent to potentially interested institutions: the European Commission, National Contact Points, Polish ministries relevant to spheres of science, education, employment, economic development, regional development, Polish Regional Labour Offices, regional authorities, universities and research institutes in Poland and abroad.

The issues raised during the conference and seminar have been included by J. Perek-Bialas into the chapter of the book to be edited by R. Schoenmaeckers - “Population ageing and the quality of life”.

The project has been mentioned in a paper on networking presented by M. Frankowicz in Athens (spring 2007, conference of ESTIA-NET); the paper will be published in the conference proceedings.
The project webpage http://www.kpk.gov.pl/triple/ has been active throughout the lifespan of the project and will be active during the 7FP.
� EMBED MSPhotoEd.3  ���











Strona 1 z 6

_1115917090.bin

