Project no.: NMP3-CT-2007-032918

Project acronym: INCOMAT

Project title: Creating international cooperation teams of excellence in the field of emerging biomaterial surface research

Instrument: Specific Support Action (SSA)

Thematic Priority 3: Nanotechnology and Nanosciences, knowledge-based multifunctional Materials; new Processes and devices (NMP)

Publishable

Final Activity Report

Period covered: from 01/03/2007 to 28/02/2009 		Date of preparation: 25/03/09

Start date of project:	01/03/2007				Duration:  24 months

Project coordinator name: 			Elke Römhild

Project coordinator organisation name:  	STIFT

Revision: 					Final Version

Table of content:

- Project execution (Summary)

  - Project objectives

  - Contractors involved

  - Work performed

  - End Results achieved

  - Methodologies and approaches used

  - Impact on industry and research sector

- Dissemination and use

Publishable results of the Final Plan for using and disseminating the knowledge

Annex 1 – Final Plan for Use and Disseminating Knowledge

Project execution

www.ssa-incomat.com

1.1. Project objectives:

- To obtain a comprehensive survey on the key resources in biomaterial research and industry in the involved regions including EU, Western Balkan Countries (WBC) and Newly Independent States (NIS)

- To form and operate four multidisciplinary cooperation Teams of Excellence (ToE) for emerging biomaterial surface technology

- To identify RTD strategies for future joint research to meet the special needs of Third countries under consideration of global research trends

- To facilitate the scientific-technological cooperation in biomaterials research between EU and US to transfer specific knowledge in this field from US to excellent European biomaterials groups

- To act as an international platform for the exchange of good practices and experiences and for the identification of cooperation opportunities between EU and INCO regions

1.2. Contractors involved:

| Role | Participant name | Country |
| --- | --- | --- |
| COO | Stiftung für Technologie, Innovation und Forschung Thüringen (STIFT) | D |
| CR | Institute for Bioprocessing and Analytical Measurement Techniques e.V | D |
| CR | Rudjer Boskovic Institute, Division of Physical Chemistry | HR |
| CR | Institute of Technical Sciences of the Serbian Academy of Science and Arts | Serbia |
| CR | Scientific-technology park “Metolit” at BNTU | BY |
| CR | Georgian Technical University, Centre for Medical Polymers and Biomaterials | GE |
| CR | E.O. Paton Electric Welding Institute of the National Academy of Sciences of Ukraine | UA |
| CR | Institute for Problems of Materials Science Kieve | UA |
| CR | IKTZ Innovative Klebtechnik Zimmermann | D |
| CR | Qserve Consultancy B.V. | NL |
| CR | Institute of Nuclear Sciences “Vinca” | Serbia |
| CR | Institute on Laser and Information Technologies RAS | RU |
| CR | University of Texas at San Antonio | US |
| CR | University of Cambridge, Department of Materials Science and Metallurgy | UK |
| CR | Institute for Low Temperature Physics and Engineering Kharkiv | UA |

Co-ordinator contact details:

Stiftung für Technologie, Innovation und Forschung Thüringen (STIFT), Peterstrasse 1,

D-99084 Erfurt, Tel. +49 361 7892376, roemhild@stift-thueringen.de

1.3. Work performed:

- Caused by changes in the partnership concerning Partner 1 and Partner 10 some modifications in the contract and the revision of Annex 1 - Description of Work (DoW) were requested and negotiated with the EC via the PO.

- According to the rules the Contract amendmend has been requested by the coordinator (final version dated 4th July 2008) and confirmed by the EC on 24th October 2008, valid from 1st March 2008 (retroactively).

- The well-established four Teams of Excellence dealing with

- Bone tissue Engineering

- Bioactive and biomimetic coatings for anhanced bone contact

- In-vitro/in-vivo testing to predict osteointegration,

- Quality assurance and certification of medical products

have collected specific data and generated high quality entries into the questionnaire. They applied a very specific tool and template to obtain relevant data and contacts in WBS and NIS.

- All partners from WBS and NIS (Croatia, Serbia, Russia, Ukraine, Belarus, Georgia) have spread the questionnaire in their regions.

- The summary on the regional analysis has been formulated (D9).

- The trend Chart on innovation in biomaterials research was elaborated (D10).

- The consortium has continued to collect research strategies among all 15 partners.

- More than 30 new project ideas (D12) were presented by rather all project partners during the project meetings and regional workshops.

- Under evaluation of the leaders of the Teams of excellence five project ideas (D13) were validated and pre-selected for later submission in RTD programmes.

- A consistent dissemination and communication strategie has been implemented. (D18).

- INCOMAT has been presented in front of 20 other coordinators of EU-projects with INCO-countries invited by the International Office/DLR in Bonn, June 2008

- Regional workshops in Herceg Novi/Montenegro and Zagreb/Croatia were supported by INCOMAT members with speaches and lectures.

- The Final Conference dealing with Biomaterial Surfaces has been prepared in the reporting period and well-organized in February 2009 in Erfurt, called as “5. International Technology Transfer Days BIOMATERIAL2009”.

1.4. End Results achieved:

- Contract amendmend: signed by the EC on 24th October 2008, valid from 1st March 2008 with revised Annex 1 (DoW revised version)

- A Summary Report on regional analysis (D9) including the technical competencies and players in Croatia, Serbia, Russia, Ukraine, Belarus, Georgia has been completed with some delay in period 2.

- The Trend Chart on Innovation in Biomaterial Science and Technology (D10) has been completed with some delay in period 2.

- Joining evaluation of the regional results during the Team Leader Meeting in May 2008 in Amsterdam and the Project meeting in September 2008 in Herceg Novi/Montenegro

- Every INCOMAT partner has undertaken a wide range of dissemination activities: further regional workshops took place in Croatia, Serbia/Montenegro and Ukraine. TV sessions could be arranged in Ukraine and Serbia via National TV channels.

- The joint Dissemination plan D18 has been elaborated as final version.

- As Highlight the “5. International Technology Transfer Days BIOMATERIAL2009” were organized successfully in February 2009 in Erfurt. It was a combination of scientific conference with key notes and a pre-planned brokerage part with fruitful individual meetings. The event attracted more than 80 people from 16 countries.

1.5. Methodologies and approaches used

The objectives of INCOMAT as defined in the work programme have been achieved by use of the following methodology and approach:

Creation of the multidisciplinary Teams of Excellence (ToE’s) led by excellent scientists and managers to secure a high-level approach in biomaterial research:

1. 	Bone tissue Engineering

Team Leader: University Cambridge (Serena Best)

2. 	Bioactive and biomimetic coatings for anhanced bone contact

Team Leader: Rudjer Boskovic Institute Zagreb (Maja D. Sikiric)

3. 	In-vitro/in-vivo testing to predict osteointegration

Team Leader: Iba Heiligenstadt (Klaus Liefeith)

4. 	Quality assurance and certification of medical products

Team Leader: Qserve (Willibrord Driessen/CEO)

All INCOMAT partners have choosen their membership in one or two Teams of Excellence under consideration of the existing research interests and future scientific issues to be implemented in the mentioned region

Elaboration of a specific questionnaire as online tool and distribution of the tool among the partners in WBC and NIS to collect regional data:

- Summarizing of the data gathered in several deliverables (D5-D8)

- Selection of the best results in the deliverables

  - D9:	Summary report on regional analysis in WBS and NIS

  - D10:	Trend chart on innovation in Biomaterial S&T

  - D13:  	Pre-selected proposals for later submission

- Presenting the results in the final meeting and conference “BIOMATERIAL 2009” in February 2009 in Erfurt/D.

- Publication of the deliverables D9 and D10 (as brochures) intended after finishing the INCOMAT project

1.6. Impact on industry and research sector

The regional analysis in the Third countries has shown some hidden knowledge in the field of biomaterial and health sector. The main results deal with the research sector, as almost all partners came from research institutes. The connections or collaboration with industry are rather low and underdeveloped.

The same result has been achieved in the regional workshops, made in Ukraine, Belarus, Croatia and Serbia/Montenegro: High interest of scientists, hartly participants from industry.

All included regions such as Ukraine, Belarus, Russia, Georgia, Croatia and Serbia have the same or similar structure: large research institutes with enormous knowledge, but no industry to use and implement this knowledge. Most research activities concerning biomaterials take place with clinics and hospitals, as clinical tests or trials only. The predominant medical device companies in above Third countries are subsidiaries of international groups or trade companies; both do not ask for or use local RTD capacities currently.

On the other hand the existing resaerch institutes seem to be well-financed by public means; the necessity to acquire collaborative research contracts with the regional or national industry is not strong enough until now. This situation is not comparable with Europe, where rsearch projects without industrial participation are inconceivable.

There is a huge potential for the future to establish more medical companies in above regions. And it will be sure, that public means for research decrease in the next years. This will increase the pressure on institutes to collaborate more with the local industry.

2. Dissemination and use

(see Annex 1 – Final Plan for Using and Disseminating Knowledge)

Exploitable results concerning the analysis of several European regions, methodologies and innovation have been derived from the development of the deliverables

- D9 - Summary report on regional analysis and

- D10 - Trend chart on innovation in Biomaterial Science and Technology.

Both deliverables have been elaborated in this reporting period, completed in month 24. All project partners have been involved as well in the data collection as the comprehensive  analysis phases, mainly supported by the Leaders of the four Teams of Excellence. Both deliverables will be provided as publishable results of the plan for using and disseminating the knowledge.

Project no.: FP6-032918

Project acronym: INCOMAT

Project title: Creating international cooperation teams of excellence in the field of emerging biomaterial surface research

Instrument: Specific Support Action (SSA)

Thematic Priority 3: Nanotechnology and Nanosciences, knowledge-based multifunctional Materials; new Processes and devices (NMP)

Annex 1

Plan for using and disseminating the knowledge

(Final report)

Period covered: from 01/03/2007 to 28/02/2009		Date of preparation: 24/03/2009

Start date of project:	01/03/2007					Duration: 24 months

Project coordinator name: 			Elke Römhild

Project coordinator organisation name: 	STIFT

Revision: 					Final version

## Annex 1 – Plan for using and disseminating the knowledge

Section 1 - Exploitable knowledge and its Use

Currently, at reporting month 24, the following exploitable knowledge or results derived from the INCOMAT project is available:

Based on the comprehensive analysis in several European regions in Eastern Europe (WBS and NIS) the main deliverables for use and publication have been developed:

- D9 Summary report on regional analysis and

- D10 Trend chart on innovation in Biomaterial Surface Technology.

The collection of the deliverables D5, D7 and D8 (completed in period 1) and the completed analysis of the respective regional scientific competencies, strengthes and best practices were count as an essential prerequisite to reach the results achieved in D9 and D10.

All project partners have been involved both in the data collection and analysis phases and in the exploitation of the project results. The main conclusions (Regional analysis report, biomaterial trend chart on innovation) will be exploited in current and future R&D activities and projects on national and European scale, because no particular agreements would prevent the wider exploitation. Due to the network character of INCOMAT appropriate IPR protection measures did not play an important role in the past project phase.

It is expected for the time beyond the project that the commercial exploitation of important project results, e.g. the publication of latest or hidden scientific results will lead to considerable positive influences in the biomaterials and health sector in Europe.

Section 2 – Dissemination of knowledge

The following tables present the most important activities related to the dissemination of knowledge and the INCOMAT project results. The detailed description of all activities is specified in deliverable D18, the dissemination plan.

The overview table comprises the following categories:

- Public relations materials (Project website, flyer and poster)

- TV sessions in period 2

- Publications in national and international scientific journals

- Major events participated

- Events organized

- Regional workshops organized

- Other network contacts

Additional remarks:

- Apart from the project website all partners inserted INCOMAT related information into their own web sites (see Deliverable D18, Dissemination plan)

- The project partners participated in several events on national and international scale to present the INCOMAT project, its contents and outcomes.

- In this context we would have to point out the active contribution to the international conferences and exhibitions in Zürich, Faenza, Kiev, Minsk, Moscow, Amsterdam, Hanover, New York, Belgrade and Tbilisi.

- The partners 7 and 11 (PEWI Kiev and Vinca Belgrade) were actively in preparing and supporting TV sessions in Serbia and Ukraine. In both regions it was possible to present some details about the INCOMAT network in front of a large audience.

- The partner P4, the Institute of Technical Sciences in Belgrade organized two important YUCOMAT conferences, mainly targeted to the Western Balkan countries:  the “9th Annual Conference on advanced materials” -YUCOMAT 2007 from 10.-14. September 2007 and the “10th Annual Conference on advanced materials” -YUCOMAT 2008 from 08.-12. September 2008, both in Herceg Novi/Montenegro (www.yu-mrs.org.yu); the latter was connected with a symposium on biomaterials with 3 invited lectures and 26 papers.

- The partners P1 – STIFT and P2 – IBA organized, supported by the other INCOMAT project partners, the final event „BIOMATERIAL 2009“, applied as a large international conference in February 2009 in Erfurt, Germany.

90 participants from 17 countries will be expected.

Section 3 - Publishable results

The main exploitable knowledge and results of the project has been covered in two documents, the deliverables D9 and D10:

D9:       Summary report on regional analysis

D10:     Trend chart on innovation in Biomaterial Surface Technology.

Printed versions of the documents will be available; further on oral presentations presenting the analysis results and the future trends in biomaterials are foreseen at national and international conferences or regional workshops. The information will be delivered first to the National and European biomaterial associations, like the ESB and biomat.net, to the National Contact Points for NMP in the EU countries, to the Federation of European Materials Societies and to the coordinator of the ICPC NanoNet project. Subsequently, the information will be made accessible to the biomaterial related enterprises and R&D institutes, either via afore mentioned organisations or directly.

The dissemination activities will be targeted to the EU 27, the Western Balkan countries and the Eastern European countries as well.

Additional partners necessary for publication:

- Cordis - PIDS

- National and European biomaterial associations, like the European Society of Biomaterials (ESB) and  biomat.net

- National Contact Points for NMP in all EU countries

- Federation of European Materials Societies

- Coordinator of the ICPC NanoNet

All mentioned partners will be requested for support to launch and distribute the result on their websites, events and other platforms.

Overview table

| Planned / actual project month or date | Type | Type of audience | Countries addressed | Size of audience | Partner responsible / involved |
| --- | --- | --- | --- | --- | --- |
| M3 – M24 | Project Web-site: www.ssa-incomat.com Continuously updated | General public | all |  | P2, P1 |
| M2 M27 | Flyer in German and English language Updated flyers with new partnership details | General public | all |  | P2 P2 |
| M4/M27 | Poster (A0): designed and printed, downloadable, updated with new partnership | General public | all |  | P2 P1 |
| M16 M21 | TV sessions Television broadcast by Serbian National TV: Presentation of VINCA institute and INCOMAT project objectives, 28. 06. 2008 , presented by Dr. Vukoman Jokanovic Round table on Ukrainian TV, channel “RADA”, 27.11.-13.12. 2008: Artificial implants and problems of their compatibility with organism”, with INCOMAT network presentation by Prof. Borisov | Generakl public Generakl public Scientists, industry | WBS NIS | Large audience Large audience | P11 P7 |
| M6 M8 M9 M9 M6 M8 M16 M16, M22 M16, M20, M22 M22 | Publications in national and international specific journals Article in the “Journal of Materials in Medicine” 10 articles published in regional publications, 2 articles in international journals, Monograph promoted at the Book Fair in Belgrade, 22.-28.Oct.2007. Russian Scientific Journal of Advanced Materials: press coverage in November 2007 INCOMAT information translated and submitted to Publishing House and newspaper “Health of Ukraine” Newspaper article “What does it mean –INCOMAT”, Weekly “All-Ukrainian Technical newspaper, 9.August 2007 Newspaper article “INCOMAT-it is a name of hope s” published in”, All-Ukrainian weekly “2000”, 19.October 2007 8 publications in international journals (e.g. Mat.Chem.Phys., Aust Dent J., Appl. Surface SCI., Biomaterials) + 11 publications in national journals 2 MSc thesis (June and December 2008) 6 articles in national scientific magazines 2 articles in international scientific magazines Preannouncement of “BIOMATERIAL 2009” in scientific magazines like: DeviceMed, BIOForum, Swiss Report for European Business & Innovation Article about INCOMAT in “Vremja” (Times) of 2nd December 2008 | Materials and medicine Medicine Materials and medicine Health Industry, Health Industry, Health Materials and medicine Materials and medicine Materials and medicine IND, RES, GOV | all all all all UA, Russia UA, Russia all all All NIS | 66.000 150.000 120.000 large | P14 P4 P12 P7 P15 P15 P11 P4 P1, P2, P14 P15 |
| M2 M4 M6 M8 M9 M9 M5 M7 M8 M9 M7 M5 M9 M8 M7 M8 M13 M14 M14 M15 M16 M17 M19 M19 M19 M20 M20 M21 M21 | Major Events participated Workshop “Problems during cleaning and sterilization of implants for hard Tissue replacement” 1.-3-April 2007, Senlis/France, Poster and oral presentation (invited by CETIM) ECM VIII: Bone Tissue Engineering, Davos/CH, 25-28 June 2007 (iba) with poster session (INCOMAT poster) and distribution of INCOMAT Flyers “Biosurf VII”-Functional interfaces for directing biological responses, 29.-31.August 2007 in Zurich/CH, with poster session (INCOMAT poster), distribution of INCOMAT leaflets Conference CCT 2007: Ceramics, Cells and Tissues, 1.-5.October 2007 in Faenza/Italy, Oral presentation, 1 page announcement of the INCOMAT project in the participants catalogue, poster session and leaflets distributed International Congress on Biohydrogels, 14.-18.Nov.2007, Viareggio/Italy, Croation Microscopy Society, Annual Meeting, 23.November 2007, Zagreb, INCOMAT presentation by Maja Sikiric INCOMAT announcement at III World Congress on Bioengineering, July 2007, Bangkok,Thailand INCOMAT announcement at IV International Conference “Supercritical Fluids: Fundamentals, Technologies and Innovations”, September 2007, Kazan, Russia, CCT 2007, 2./3. October 2007 in Faenza: 2 thesis of IPMS (made by V. Dubok) and Oral presentation: scientific thesis of P11- Vinca (made by M.B. Plavsic) Ukrainian Conference on nanomaterials and nanotechnology , 21-23.November 2007, Kiev: Poster session about INCOMAT made by Prof. Dubok Seminar “Preparation of experts in the field of innovative activity”, 27.-28.September 2007, Minsk/Belarus Internationale Biomaterialtage, 6.-7.July 2007, Munich/Germany Annual conference of the German Society of Biomaterial, 22.-24-Nov. 2007, Hanover/Germany 15th International exhibition “Medicine-2007 Medtech. Phamaceutics. Dentistry” to distribute INCOMAT information like the leaflet and the Informational booklet (Minsk, October 2007) http://www.minskexpo.com.by/eng/medicine2007/ 1st International Caucasian Symposium on Polymers and Advanced Materials, Tbilisi, Georgia, 10-14 Sept. 2007 International Conference “New Polymers and Radioprotectors for Biology and Medicine”, Yerevan, Armenia, 8-10 October 2007 Conference “Actual problems in endosprosthetics”, Vinnica/UA, 13-14 March 3008 6th world meeting on pharmaceutics and biopharmaceutics” in Barcelona; April 2008 15th International specialized exhibition «HEALTHCARE IN BELARUS – 2008» ; Minsk, 01.04 - 04.04.2008 by the leaflet and informational poster 8th World Biomaterials Congress in Amsterdam / NL, May 28 - June 1, 2008 III.” International conference on Medical Physics and Innovation” in Moscow, June 2008 35th Annual Meeting & Exposition of the controlled Release Society, New York, USA, 12.-16.July 2008 PHYSICAL CHEMISTRY – 9th international conference, Belgrade, 24.-26. September 2008 INCOMAT announcements and leaflets distribution at the German-Ukrainian Symposium on Nanosciences and nanotechnology, Essen, Germany, 22.-25.Sept. 2008 CRDF-RESC conference, Aghveran, Armenia, 21.-24.Sept. 2008 16th International exhibition “MEDICINE-2007- MEDTECH. PHARMACEUTICS. DENTISTRY”, Minsk, 30 September - 3 October 2008 International specialized exhibition «Belarus Dent», Minsk, 28-31 October 2008 Annual meeting of Croatian Microscopy Society; 28.11.2008 BONE-TEC international conference in Hannover/ Germany; 7.-9.11.2008 | Health, tissue engineering Bone tissue engineering Biomaterial surface research Nanotechnology, regenerative medicine Surgery, Drug delivery systems, tissue engineering Medicine Biotechnology Health Nanotechnology, regenerative medicine Nanotechnology Innovation Research in Biomateriasl Research in Biomaterials Medicine, dentistry Materials Biology, Medicine Materials, medicine Pharmaceutics, Biopharmaceutics Healthcare Biomaterials Medicine, Physics Medicine Chemistry, Materials Nanotechnology Chemistry, Biology, Medicine Medicine Dental medicine Medicine, Microscopy Biomaterials | all all all all all Croatia all all all Ukraina Belorus all Germany all all all NIS all Russia, Belarus all all USA WBC Germany, Ukraina Georgia, Armenia all Belarus, Russia Croatia all | 500 250 160 | P2 P2 P2 P2 P2 P3 P12 P12 all P8 P5 P1 P1 P5 P6 P6 P7 P12 P5 P2, P3, P4, P14 P12 P4 P4 P8 P6 P5 P5 P3 P2 |
| M10 M13 M16 M17 M20 M7 M19 M22 M24 | Other network contacts 6th Young Researchers Conference, 24.-26. December 2007, Belgrade, INCOMAT session presented Conference “nanotec 2008”, 10.-13. Mar 2008, Venice/Italy: poster session, flyers distributed in the workshop on 13. March 2008, organized by the IRC network International workshop (26th June 2008 in Bonn/D) More than 20 coordinators from other INCO- projects were attendant with similar project presentations. This workshop was an excellent opportunity to contact coordinators from Russia and other NIS. It was an efficient platform to spread information about the Final conference BIOMATERIAL2009 and to install some links. Medizin Innovativ – Forum Biomaterials, Nuremberg, Germany, 9.7.2008 Meetings of national/international medical associations and interest groups, like IRC/IRE regional networks MATERIALICA 2008 – International Congress and fair, Munich, 16. October 2008 Events organized YUCOMAT 2007: “Annual Conference on advanced materials” Symposium E: Biomaterials with 3 invited lectures and 40 papers, 10.-14. September 2007 in Herceg Novi/Montenegro (www.yu-mrs.org.yu), INCOMAT leaflet disseminated, poster session, report published MRS Bulletin, Vol.32No.12(2007) and in TEHNIKA, No.5 (2007) in Serbian language YUCOMAT 2008: The 10th Annual Conference YUCOMAT 2008 “Annual Conference on advanced materials” 8.-12. Sept. 2008, Herceg Novi / Montenegro (www.yu-mrs.org.yu Symposium E - Biomaterials with 5 invited lectures and 26 papers, INCOMAT leaflet disseminated, poster session; two additional workshops organized 7th Young Researchers Conference, 22. - 24. December, Belgrade. It included 2 sessions dedicated to biomaterials and biomedical engineering related to the INCOMAT project Final Event “BIOMATERIAL 2009, Erfurt, Germany, 19. / 20.Febr. 2009 5th International Technology Transfer Days for Biomaterials with 90 participants of 17 countries | Research Nanotechnology EECA coordinators Medicine Materials Research in materials Research in Biomaterials Biomaterials Biomaterials | Serbia Europe EECA Europe all all all Serbia all | 25 | P4 P1 P1 P2 P1 P4 P4, all P4 P1, P2 responsible (all other partners involved) |
| M15 M19 M20 M22 M22 | Regional workshops 4. Congress of Ukrainian neurosurgeons, Dnepropetrowsk, Ukraina, 27.-30.May 2008; Regional workshop INCOMAT Regional INCOMAT workshop for Western Balkan Countries during the YUCOMAT conference 2008 in Herceg Novi / Montenegro, 10. September 2008 Ukrainian Scientific conference “Biomaterials in Orthopedy and Traumatology”, Kharkiv, Ukraina, 1.-4.Oktober 2008, Regional workshop INCOMAT Regional workshop Thüringen, Meeting of the “Thuringian Regional Working Group Biomaterials” , Mörsdorf, Thüringen, D 04.12.2008, (Promotion of INCOMAT, Acquisition Final conference BIOMATERIAL 2009) Regional Dissemination Workshop “Project INCOMAT connecting biomaterials experts”, Zagreb, Croatia, 19.12.2008 (50 Participants, incl. P1, P3, P4, P10, P11 ) | Neurosurgery Biomaterials Orthopedy Biomaterials Biomaterials | Ukraine WBC Ukraine Thüringen WBC |  | P8 P4 P8, P15 P1,P2 P3 / P1,4,10,11 |