Project no.: LSHC-CT-2003-506803

Project acronym: INTACT

Project Title: Identification of Novel Targets for Cancer Therapy

Instrument:  Integrated Project

Thematic Priority: Life sciences, genomics and biotechnology for health

3rd Periodic Management report

Period covered:  1.1.2006-31.12.2006		Date of preparation:

15.2.2007

Revised: 11.12.2007

Start date of project: 1.1.2004			Duration: 4 years

Project coordinator name:  Kristian Helin

Project coordinator organization name: University of Copenhagen (UKBH)

INTACT research coordinator name (editor): Pia Klausen

INTACT financial manager name: Johanna Tara Bowns Poulsen

Section 1 – Justification of major costs items and resources	3

Partner 1 (UKBH): WPs 7, 15, 29	3

Partner 2 in Total (NKI1, NKI2, NKI3)	4

Partner 2 (NKI1): WPs 5, 26	5

Partner 2 (NKI2): WPs  12, 24	6

Partner 3 (CNIO1) : WP 8, 9, 16	8

Partner 3 (CNIO2) : WP 20	9

Partner 4 (GEM): WPs 18, 30	10

Partner 5 (MDC): WP 25	11

Partner 6 (UNIMAR): WPs 21, 22	12

Partner 7 (ISREC1, ISREC2): WPs 23, 6	13

Partner 8 (BICR): WPs 10, 11	14

Partner 9 (Pasteur): WP 19	15

Partner 10 (Morphochem): WP 28 - closed	16

Partner 11 (Agendia): WP 27	17

Partner 12 (IEO): WPs 4, 13, 17	19

Partner 13 (Vichem): WP 32	20

Summary explanation of the impact of major deviations from budget	22

Partner 4 (GEM): WPs 18, 30	22

Partner 7 (ISREC1, ISREC2): WPs 23, 6	22

Partner 8 (BICR): WPs 10, 11	22

Partner 11 (Agendia): WP 27	22

Partner 13 (Vichem): WP 32	22

Section 2 – Form C Financial statements for all partners	23

Section 3 – Summary financial report	24

# Section 1 – Justification of major costs items and resources

## Partner 1 (UKBH): WPs 7, 15, 29

##### RESEARCH AND TECHNOLOGICAL DEVELOPMENT ACTIVITIES

Personnel

One full-time post-doc (fellow) was appointed to continue the work on WP 15 dealing with the establishment of cell culture high-throughput screening robotic systems, reporter cell lines for screening for inhibitors of E2F function.

Total personnel cost: € 65,369.60

Consumables

A total net amount of € 29,374.41 was spent to purchase lab consumables, subdivided in the following categories:

| - Molecular biology | € | 1,496.61 |
| --- | --- | --- |
| - Proteins and antibodies | € | 1,854.23 |
| - Cell culture | € | 1,327.06 |
| - Chemicals | € | 4,297.88 |
| - Mice and rabbits | € | 1,693.46 |
| - DNA Oligoes | € | 589.81 |
| - Enzymes | € | 224.90 |
| - plasmid DNA purification kits | € | 17,890.46 |
| - Total | € | 29,374.41 |

Equipment

No equipment was bought in 2006

Total research and technological development costs: € 94,744.01

##### MANAGEMENT ACTIVITIES

One full time research coordinator worked full time on WP 29 from January to February.

In April 2006 a new research coordinator was hired full time to work on WP 29.

Total personnel costs:  € 43,103.74

A total amount of € 17,744.10 was spent on travel costs and management activities related to the INTACT project.

The costs for the Audit certificate ( € 1,000.00) will relative to 2006 appear in 2007.

Total management costs: € 61,848.84

## Partner 2 in Total (NKI1, NKI2, NKI3)

##### RESEARCH AND TECHNOLOGICAL DEVELOPMENT ACTIVITIES

Personnel 				               € 238.565,01

Consumables

Total:	449.982,32

Overhead:		                                           	                    90.324,46

Grant total:	541.946,78

Equipment	0

No equipment was bought in 2006

Total research and technological development costs:	€  440.194,17

Training Costs	€      9.788,00

##### MANAGEMENT ACTIVITIES

Total management costs:

The costs for the Audit Certificate relative to 2005  	€      1,640.00

## Partner 2 (NKI1): WPs 5, 26

##### RESEARCH AND TECHNOLOGICAL DEVELOPMENT ACTIVITIES

Personnel

Two post-docs fellows (J.A. Boren and H.I. de Vries) were appointed to characterize the lentiviral based pathway regulation in in vivo mouse models (WP5) and the role of distinct cancer pathways in the resistance to therapy (WP26) participant 3 (NKI1).

Consumables

Consumables:

Chemicals and Molecular biology reagents	€  66.710,3

Disposables	36.486,65

general laboratory costs                               	+	35.386,14

Total incl BTW			                  138.583,09

Total w/o BTW	  		                   116.456,38

Travel costs:	       				 7490,04

Total personnel costs	      +	72.836,05

Total:	196.782.47

Overhead:		                                           	                    39.356,49

Grant total:	236.138,96

Equipment

0

## Partner 2 (NKI2): WPs  12, 24

##### RESEARCH AND TECHNOLOGICAL DEVELOPMENT ACTIVITIES

Personnel

One post doc worked on WP24 (P.Eichorn, NKI2). 1.1 fte PhD students (H. Oosterkamp and R. Kortlever) worked on WP 12 and 24 of NKI2 (participant 4)

Consumables

Consumables:

Chemicals and Molecular biology reagents	€  65.466,88

Disposables	0,00

general laboratory costs                               	+	2.387,52

Total incl BTW			                    67.854,40

Total w/o BTW	  		                     57.020.50

Travel costs:	       				363,28

Total personnel costs	      +	95.240,35

Total:	152.624,13

Overhead:		                                           	                    30.524,83

Adjustments to previous periods

Grant total:	183.148,96

Equipment	0

Partner 2 (NKI3): WPs 14

##### RESEARCH AND TECHNOLOGICAL DEVELOPMENT ACTIVITIES

Personnel

Two fellows (A. Pietersen and P.M. van der Stoop carried out the work described in WP14 for NKI3, participant 5

Consumables

Consumables:

Chemicals and Molecular biology reagents	€  23.823,12

Disposables	2.028,01

general laboratory costs                               	+	7.650.08

Total incl BTW			                    33.501,21

Total w/o BTW	  		                     28.152,28

Travel costs:	       				1.934,83

Total personnel costs	      +	70.488,61

Total:	100.575,72

Overhead:		                                           	                  20.115,14

Grant total:	120.690.86

Equipment	0

## Partner 3 (CNIO1) : WP 8, 9, 16

##### RESEARCH AND TECHNOLOGICAL DEVELOPMENT ACTIVITIES

One part of the resources was dedicated to the development, technical improvement and exhaustive validation of a reliable high-throughput method for telomere length measurements.

The other part was used to investigate the relevance of the siRNA pathway, in particular the role of Dicer, for the regulation of telomere function at the epigenetic level.

Personnel		42.294,84 €

Consumables	140.450,07 €

Equipment

Indirect Costs                 38.839,8 €

Total research and technological development costs: 182.744,91 €

##### MANAGEMENT ACTIVITIES

900 € Audit

#### Total management costs: 900 €

## Partner 3 (CNIO2) : WP 20

##### RESEARCH AND TECHNOLOGICAL DEVELOPMENT ACTIVITIES

A small part of the resources was used to finalize our work on an shRNA screening aimed at the identification of novel inhibitors of

E2F1 and the functional validation of oncogene-induced senescence markers. The major part of the resources was dedicated to the identification of novel mechanisms implicated in the epigenetic regulation of the Ink4a/Arf locus.

Personnel		65.203,08 €

Consumables	140.450,07 €

Equipment

Indirect Costs                 38.839,8 €

Total research and technological development costs: 244.492,95 €

##### MANAGEMENT ACTIVITIES

900 € Audit

#### Total management costs: 900 €

## Partner 4 (GEM): WPs 18, 30

##### RESEARCH AND TECHNOLOGICAL DEVELOPMENT ACTIVITIES

Personnel

One full-time post-doc continued to characterize the effect of B-Raf and Raf-1 on tumorigenesis in vivo and in vitro; a second post-doc was supported for two months prior to being transferred to another contract (2 + 12 ; € 59,620.52).

Consumables

A total net amount of € 28.309,51 was spent to purchase lab consumables, subdivided in the following categories, and for travelling to the 2nd INTACT Symposium in Madrid:

| - Molecular biology reagents, antibodies, cell culture reagents, plastic and glassware, general supplies | € | 20.486,66 |
| --- | --- | --- |
| - Mouse genetics | € | 7,289.63 |
| - Travel expenses | € | 533,22 |

Equipment

None purchased

Total research and technological development costs: € 87,930.03

##### MANAGEMENT ACTIVITIES

A secretary (€ 12.931) assists with management tasks (WP 18 + WP 30).

One secretary was employed (15 hrs/week) from January 1st to June 1st From June 1st to July 14th 2006, a second secretary was employed on the contract (25 hrs/week total). Since the secretary employed originally was leaving, this was done to ensure a smooth transition. Thereafter, secretarial help has been reduced to 10 hrs/week.

A total amount of € 1,884.94 was dedicated to travel costs related to the 2nd INTACT Symposium in Madrid and to Steering Committee Meetings.

The costs for the audit certificate relative to 2005 amount to € 1,350.

The costs for the Audit Certificate relative to 2006 will appear on next year’s cost management report

Total management costs: € 16,165.94

## Partner 5 (MDC): WP 25

##### RESEARCH AND TECHNOLOGICAL DEVELOPMENT ACTIVITIES

Personnel

A total amount of 24.526,83 EUR personnel costs for 2 doctorands.

Consumables

A total amount of 358,53 EUR was spent to purchase lab consumables.

Equipment

A total amount of 434,49 EUR was spent on equipment.

Travel

A total amount of 167,46 EUR was spent on travel costs related to the EU Meeting in Madrid, 25.-27.1.2006.

Overhead

20 % of all costs

Total research and technological development costs: 25.487,31 €

##### MANAGEMENT ACTIVITIES

The costs for the Audit Certificate (2. period) is amounting to 1.495,00 EUR and the costs for the 3. period amounting to 260,00 EUR will appear in 2008.

Total management costs: 1.495,00 €

## Partner 6 (UNIMAR): WPs 21, 22

##### RESEARCH AND TECHNOLOGICAL DEVELOPMENT ACTIVITIES

Personnel

One PhD-student (WP 21: Targeting the Myc/Miz pathway using RNAi and ERMtagbased screens (12 months; €23.043,63)

Consumables

A total net amount of € 47.753,58 was spent to purchase lab consumables, suvdivided in the following categories:

- Molecular biology reagents,

antibodies, cell culture reagents,

plastic and glassware, general

supplies	47.620,91€

- Travel expenses	132,67€

Total research and technological development costs: € 70.797,21

##### MANAGEMENT ACTIVITIES

- The costs for the Audit Certificate

relative to 2006	817,43€

- Overhead	14.159,44€

Total management costs: € 14.976,87

## Partner 7 (ISREC1, ISREC2): WPs 23, 6

##### RESEARCH AND TECHNOLOGICAL DEVELOPMENT ACTIVITIES

Personnel	€  76’793.36

Consumables	€  17’429.27

Equipment	-

Total research and technological development costs:	€ 94’272.63

##### MANAGEMENT ACTIVITIES

Total management costs:	€ 702.24

## Partner 8 (BICR): WPs 10, 11

RESEARCH AND TECHNOLOGICAL DEVELOPMENT ACTIVITIES

Personnel

There were two full time post-doctoral scientists engaged on this project until 31/03/06 and one post-doctoral scientist and one principal scientific officer thereafter.

Total personnel costs: €145’273.12

Consumables

A total net amount of €50’285.52 was spent to purchase lab consumables subdivided into the following categories:

| General Chemicals | €15’207.48 |
| --- | --- |
| Biochemicals | €13’164.25 |
| Antisera and Proteins | €6’852.18 |
| Glassware and Plastics | €5’178.22 |
| Oligos | €3’807.58 |
| Miscellaneous Lab Consumables | €3’723.06 |
| Nucleic Acids and Kits | €1’547.97 |
| Small Lab Equipment | €360.13 |
| Tissue Culture | €307.08 |
| Radiochemicals | €137.57 |

Total                                             €50’285.52

Equipment

There were no major items of equipment purchased.

MANAGEMENT ACTIVITIES

The cost of the audit certificate was: €707.74

Overhead

20 % of all costs: €39’111.72

## Partner 9 (Pasteur): WP 19

##### RESEARCH AND TECHNOLOGICAL DEVELOPMENT ACTIVITIES

Personnel

One full-time post-doc (fellow) was appointed since April 15, 2005 to isolate genes that are involved in senescence of human embryo fibroblasts in which PML is overexpressed (WP19). The screen led to the isolation of 80 clones from which DNA could be retrieved. 35 clones have been analyzed for their shRNA content. 10 of them were selected for validation experiments.

Total personnel costs :	 € 46 796.37

Consumables

A total net amount of € 74 055.18 was spent to purchase lab consumables, subdivided in the following categories :

- Molecular biology reagents	€	43 788.91

- Oligonucleotides		€	11 826.24

- Other costs		€	18 440.03

Equipment

A Coulter cell counter was bought in June 2005, in order to accurate assess proliferative capacity of infected  cell populations. Depreciation for 2006 : € 2 625.60 (included in: Consumables, Other costs)

Indirect costs	€ 24 170.31

Please note that the depreciation for 2005 (€ 1 545.82), that was not included in the form C for 2005, has been taken in account in the form C for 2006:

adjustments costs + indirect costs: 	€ 1 854.98

Total research and technological development costs: € 146 876.84

##### MANAGEMENT ACTIVITIES

A total amount of € 1 100 was spent for the Audit Certificate

Total management costs: € 1 100.

TOTAL COSTS : 	€ 147 976.84

## Partner 10 (Morphochem): WP 28 - closed

## Partner 11 (Agendia): WP 27

Cost justifications:

Agendia participates in work package 27

##### RESEARCH AND TECHNOLOGICAL DEVELOPMENT ACTIVITIES

Personnel

The following personnel was involved in INTACT WP27 in 2006

Name			Title		involved (person-months)

R. Bernards			CSO			0.5

L van ‘t Veer			COO			0.1

A. Glas			Head Bioinformatics		1.2

M. Warmoes			Bioinformatics		3.9

T. Bruinsma			Bioinformatics		6.3

R. van Laar			Bioinformatics		3.3

O.Krijgsman			Bioinformatics		1.0

A. Floore			Head Technician		1.0

J. Lahti			Technician			0.0

L. Delahaye			Technician			0.1

A. Schuurman		Technician			0.8

M. Pater			Technician			0.5

A. Witteveen			Technician			1.2

R. Pover			Technician			0.5

L. Stork			Clinical Trial Man.		0.1

B. van der Baan		Bus. Dev. Manager		2.5

I. Simon			PM Scientific		0.4

Total	   					23.4

The planned effort for the 48 months project was 96 person-months total (of which 48 funded by INTACT). As described in the scientific progress report, we have nearly completed all tasks which were planned for the first 36 months (older age breast cancer, Lymphoma and Lung) of WP27 and are well underway in further work to be done on especially Lung and the Resolver implementation. We therefore feel that the involvement of the personnel in 2006 was adequate and justified, considering the progress made by the partner.

In brief, the CSO, COO, Project Manager Scientific and Business Development Manager were involved in planning the projects, setting up the academic network for the lung project and in selecting tumor samples from the tumor bank. The technicians were involved in isolating the RNA from the tumor samples and the performing of tests and the bio-informaticians were involved in setting up the database and in the data analysis of the micro-array experiments.

Consumables

There have been costs of consumables charged to this project in the third 12 months of the project. The costs refer to the direct material costs of the micro-arrays used in the development of the lung profile. 90 tumor samples were tested at direct material costs of EUR 80K. EUR 25K of these consumables have been carried by Agendia.

Equipment

Agendia has been heavily investing in equipment to be able to perform the tests in order to meet the strictest quality requirements. 4% of the maintenance & depreciation expenses have been charged to INTACT to be able to perform the tests. Further the direct costs and depreciation expenses of the Resolver project (setting-up of the database of gene expression signatures) have been charged to the project. As the latter was not done for 2005, a correction for previous years has been reported.

## Partner 12 (IEO): WPs 4, 13, 17

##### RESEARCH AND TECHNOLOGICAL DEVELOPMENT ACTIVITIES

Personnel

One lab technician (fellow) optimised the substrate with specific treatment to obtain localised and efficient infection of GFP reporter genes in primary and cancer cells (WP4).

One full-time post-doc (fellows) was dedicated to identify regulators of the p53 pathway, focusing on p53-regulation in hematopoietic stem cells, and to analyze the physiological function of NPM and the biological properties of AML-associated NPM mutants (WP13 and WP17).

Moreover, a full time technician kept working on cell culture procedures.

Total personnel costs: € 49.576,36

Consumables

A total net amount of € 44.690,54 was spent to purchase lab consumables, subdivided in the following categories:

| - Molecular biology materials | € | 17.282,62 |
| --- | --- | --- |
| - Oligonucleotides | € | 1.631,95 |
| - Antibodies | € | 10.148,44 |
| - Enzymes and kits | € | 6.745,00 |
| - Plastic and glassware | € | 8.882,53 |

Travel

A total amount of € 500,30 was spent for the participation to the project annual meeting.

##### MANAGEMENT ACTIVITIES

A total amount of € 2.000,00 was spent for the Audit Certificate.

## Partner 13 (Vichem): WP 32

##### RESEARCH AND TECHNOLOGICAL DEVELOPMENT ACTIVITIES

Personnel

| Name | % of time on Project | Amount € |
| --- | --- | --- |
| György Kéri, Dr. | 240 % | 9 596 € |
| Bálint Hegymegi - Barakonyi | 408 % | 5 840 € |
| Csaba Szántai-Kis | 360 % | 5 185 € |
| Zsolt Szekelyhidi | 525 % | 8 086 € |
| Ildikó Szilágyi, Dr. | 283 % | 11 560 € |
| Jenő Marosfalvi | 300 % | 7 611 € |
| István Varga | 480 % | 10 416 € |
| Zoltán Greff, Dr. | 550 % | 17 674 € |
| Zoltán Horvát | 275 % | 6 485 € |
| Erika Török | 969 % | 10 090 € |
| Frigyes Wáczek | 150 % | 3 010 € |
| László Máté | 210 % | 2 621 € |
| Total |  | 98 173 € |

In the first reporting period Vichem used 47,5 personmonths with the cost of  98.173 €.

Consumables

The consumables we purchased consist of chemicals (mainly) and laboratory equipment.

These costs were altogether 28.308 € during 2006.

Equipment

No durable equipment was purchased.

Total research and technological development costs: 126.481 € (exluding overheads)

##### MANAGEMENT ACTIVITIES

Cost of audit certificate: 1.500 €

No other management activity.

Total management costs: 1500 €

## Summary explanation of the impact of major deviations from budget

### Partner 4 (GEM): WPs 18, 30

In 2006, Participant 8 has transferred 26,741.78 Euros from the Management budget to the Research and Development budget. This deviation from the original cost plan has been discussed with the Co-ordinator during the 2nd annual meeting in Madrid (January 2006) and has been made necessary by to the high workload and consumable costs associated with the Research and Development project carried out by Participant 8.

### Partner 7 (ISREC1, ISREC2): WPs 23, 6

ISREC 2 : The postdoctoral on this position left in November 2006 and could not be replaced before the end of the year

ISREC 1 : A new PhD-Student had been hired during that period

Since this contract has been signed before January 2004,  the partners ISREC 1 and 2 are funded by the Swiss Government and not the European Commission. As agreed, a detailed financial report will be sent to the Swiss Governement in March 2007 and a copy will simultaneously be addressed to the INTACT coordinator.

### Partner 8 (BICR): WPs 10, 11

The original post-doctoral scientist engaged on the grant left on 31/03/06.  Due to the difficulty in making a satisfactory new appointment for the short remaining term of the project we needed to redeploy an experienced principal scientific officer to complete the work within the required timescale.  The increase in the pay cost reflects the increase in the experience brought to the project by the scientific officer.

### Partner 11 (Agendia): WP 27

The Resolver software is now installed and currently being further developed and upgraded. The setting-up of the database has been delayed by about half-year. As the software is now installed and currently being further developed and upgraded, we expect it to finalize in 2007. The main aims of the work packages in which Agendia was involved were accomplished.

### Partner 13 (Vichem): WP 32

The number of person-months increased, since we had to assign additional human resources for the synthetic efforts, because many of the planned intermediates were not available commercially, therefore we had to synthetise them in our lab. Due to this the costs of consumables were constantly lower than expected.

# Section 2 – Form C Financial statements for all partners

Form Cs for all partners are appended to the end of the document

# Section 3 – Summary financial report