|  | EUROPEAN COMMISSION RESEARCH DIRECTORATE-GENERAL Directorate F - Health F2 – Medical and Public Health Research |
| --- | --- |

REGISTERED MAIL

Brussels, 21/11/07

F2/JvdL D(2007)

Re:	Contract LSHC-CT-2003-503233 / INTACT

Comments to report for period from 01/01/06 to 31/12/06

Dear Kristian,

With reference to the 3rd report for the period from 01/01/06 to 31/12/06, received on 14/06/2007 for the above mentioned contract, we are obliged to inform you that the payment request cannot be processed since:

- The information in the periodic management report is incomplete. Justification of costs for partners NKI (subdivided for partners NKI1, 2 and 3), BICR and CNIO (subdivided for partners CNIO 1 and 2) is incomplete. Please, may I ask those partners to justify the costs incurred in relation to the data described for period 3. Please, could I receive information on "deviations", if any, for all partners. Please, could the consortium submit a revised management report.

- The level of detail in the periodic activity report (PAR) is often insufficient to assess progress and justify the costs incurred for several partners. Despite a continued and impressive number of publications in high-impact journals by individual members of the INTACT consortium, my previous remarks and a suggestion from the coordinator to all partners on this issue (2nd annual periodic activity report, pages 130-131), contents are heterogeneous, often discontinuous from data reported in period 2 and often lack scientific detail. References to published work from the partner (or to show the state-of-the-art) to illustrate progress obtained for task X or deliverable Y are absent. Collaborative efforts are not (well) described.

- Please, find below a non-exhaustive list with remarks on the PAR:

- Several groups have successfully performed screening assays in different in vitro models using the NKI siRNA library (and other libraries), but will the resulting targets be truly validated? Validation efforts should be stepped up and include existing mouse tumour models within, and if necessary obtained outside of the consortium (for example for partner ISREC2 in WP6). See also INTACT's specific objective 3: " To use existing and generate novel mouse models and non-invasive tumour imaging to validate and assay cancer gene function in vivo and to develop new treatment modalities." The SMEs could have been more instrumental in this important but unfulfilled INTACT objective. Apart from one partner, no patent protection has been sought since the start of INTACT.

- WP5: deliverables were partially changed and not entirely updated for period month 25-42 (page 20). Similar activities were and are still ongoing in WP6, but both partners do not seem to communicate on those issues (at least absent in the report). WP5 has generated a novel vector with artificial P53 responsive elements and combined it with mutated LoxP sites. Might these mutations not lead to only partial Cre excision in the mouse model? Partner ISREC2 mentioned problems with their Cre-based induction system. Is this reason for concern?

- WP6: Rather than continuing attempts to generate a xenograft model, the last 8 months and EC funds could be used to "asses the impact on tumour growth and morphology of any gene of interest" (page 25); which genes will be validated?

- WP7: Where's the evidence that "our results suggest that NEK11 is a potential tumour suppressor"? What proteins were subjected to MALDI (T7.14), how were those experiments performed and what was the outcome? What's meant with "if time allows we will further characterise the 3 other genes previously isolated and validated"? Why is it necessary to perform yet "another genome-wide screening" for G2/M regulators with so many candidates around but not truly validated?

- WP8: Progress in period 2 was very modest. This WP reports no progress at all and did not propose a contingency plan. Deliverables were not updated for month 25-42.

- WP9: There seems to be very little if any progress compared to period 2 related to INTACT's main objectives. Deliverables were not updated for month 25-42.

- WP12: Several partners report not having been able to use the siRNA library despite the fact that the report claims the library has now been sequence-verified. Thus, it's surprising that even NKI2 has revised its strategy and instead of using their own siRNA library opted to use a different screen in the HCT116 cell line. What's the reason for the change?

- WP14: Apart from NKI3 which has shown a proof of principle, the rest of the consortium seems to have abandoned the ERMtag technology (see for example WP15).

- WP15: this WP only reports on a HT screen that was performed, but does not provide any details or report on the outcome obtained sofar.

- WP16: data reported for this WP seem to partially overlap those reported for period 2. Again, there are no attempts to validate previous hits and establish their role in cancer. Together with the minimal progress for WPs 8 and 9 reported during the past three years, there's reason for concern.

- WP17: NPM-ALK has been around for a long time and it seems that part of the data mentioned for NPM-ALK were in the public domain before the reporting period started. There are no attempts to validate the importance of NPM-ALK (either alone or in combination with c-Myc) as a potential target for AML or ALCL targeted therapy or as part of tackling resistance mechanisms to chemotherapy (see for example Hsu et al, Cancer Invest 25(4):240-8). Out of the 13 tasks proposed since the beginning of the project, 4 were cancelled, two were not started yet (not explained) and one not reported on (T17.8). Alternatively, NPM-ALK dependent pathways could have been addressed  by microarray analyses in collaboration with Agendia.

- WP18: this WP has been focusing on Raf1 - Roc-α interactions in order to understand and validate Raf-1 and downstream targets. The data mention epithelial tumours, but it's not clear what tumours are referred to and if they resemble human melanoma for example. Have these tumours been analysed by a mouse pathologist? This interaction would be a logical target for screens run by VICHEM, but this is not attempted or described. Has the importance of this interaction been validated in epithelial tumours induced by existing recombinant animal models (as opposed to carcinogenesis-induced models)? Would it be of interest to analyse the role of Raf1 signalling in inflammatory processes?

- WP20: it's not clear why yet another shRNA screening was performed to identify novel E2F1 regulators.

- WP21: Usp28 is mentioned as a potential drug target, but this is not followed up in the last 18-month implementation plan. The large number of Usp-deubiquitinating enzymes currently known would make it difficult to target specifically Usp28. Usp28 might be a potential biomarker for prognostic or diagnostic purposes, but this opportunity seems to have been overlooked by the consortium (Fig 6 page 78 does not provide info on staging of tumour, % of tumours that are positive in a retrospective study or whether other tumour types show the same phenomenon, but more details are mentioned in a very interesting joint publication (Popov et al., Nat Cell Biol 9, 765 - 774).

- WP23: interesting data. Why does IEO not collaborate with this partner (WP13)?

- WP24: very similar to PAR for period 2. The new data are composed of an Iressa screen but details on the hits and initial validation is missing. There's also no mention of a possible follow-up of the Nutlin and SAHA data.

- WP26: will this WP also generate mesothelioma cell lines from patients for extensive comparison and validation (i.e. is the mouse model mimicking the disease in humans)? It seems that the report for this WP is incomplete (page 98).

- WP27: partner Agendia has the intention to generate a database with publicly available microarray expression data and signatures. What's the added value over existing database and when would such a database be operational? Fig 2 is missing, but was part of the previous PAR. Will the prognostic NSCLC signature be validated? Idem for the signatures mentioned previously.

- WP32: will any of the partners validate the identified targets? What about screening for NEK-11 substrates?

- The updated implementation plan for month 37-54 could have included a more detailed and more complete self-evaluation with references to the state-of-the-art, especially when new tasks are started (and previous ones abandoned due to technical problems). WP6 has not updated its deliverables, but proposes to enrich colon cancer initiating cells based on the CD133 marker to be used in their xenograft model. 1. it seems this partner underestimates the practical problems associated with identifying and characterising cancer stem cell and cancer initiating cell populations; 2. according to data described in the 3rd PAR the model has not yet been established.

- The integration of both SMEs AGENDIA and VICHEM with the rest of the consortium remains dubious. Is there any concrete link between the mesothelioma and lung cancer subprojects?

Consequently, the delay for approval/payment is suspended from the date of this letter until the date of approval of complete reports.

Thank you for submitting the requested information as soon as possible and in any case within 7 days from the date of this letter.

Yours sincerely,

Jan-Willem van de Loo, PhD