SSPE-CT-2004-503604

MEACAP

Impact of Environmental Agreements on the CAP

Specific Targeted Research

8.1 Sustainable management of Europe’s natural resources; modernisation and sustainability of agriculture and forestry

Final Activity Report

Period covered: 	From 1 April 2004 to 30 June 2007

Date of preparation: 	June 2007

Start date of project:	1 April 2004				Duration: 39 months

Project Coordinators: David Baldock and Tamsin Cooper

Institute for European Environmental Policy

# Project Execution

The MEACAP project is a Specific Targeted Research Project with FP6 funding that commenced on 1 April 2004 and concluded on 30 June 2007. The project was coordinated by the Institute for European Environmental Policy (IEEP), UK and involved eight other organisations from six different Member States, as follows: the German Federal Agricultural Research Centre (FAL), the German Institute for Energy and Environment (IE), Alterra (the Netherlands), the Czech Institute of Forest Ecosystem (IFER), the Italian Fondazione Eni Enrico Mattei (FEEM), the European Forest Institute (EFI) (Finland) and Humboldt University of Berlin (HUB), with input from the Scottish Agricultural College (SAC).

The project had four primary objectives:

- 1. To assess the exact obligations falling on the Community with respect to agriculture in the fulfilment of commitments under the Kyoto Protocol and the Convention on Biological Diversity (CBD), clarifying how agriculture and forestry could contribute to meeting these obligations relative to other sectors of the economy and land users.

- 2. To undertake an analysis of the most appropriate adaptations and innovations in the agricultural sector required to meet the new objectives and obligations.

- 3. To assess the extent to which changes at the farm level and upwards require alterations in policy, both at the national and EU levels. Policy change may be needed in the environmental, agricultural, forestry, research, regional support, or other policy domains. The main focus was on agricultural and rural development policies, especially those within the CAP. Specific measures of relevance to the new Member States are to be identified.

- 4. To complete and disseminate an integrated strategy for the implementation of the two agreements in the EU agricultural sector, including concrete policy recommendations applicable at a European level. The strategy combines the required responses for both the CBD and the Kyoto Protocol.

The research was also intended to contribute to the body of scientific research on the effectiveness of international environmental agreements, and on the interaction between international agreements and EU policy.

The project has its own dedicated website on which all project deliverables are available as well as the presentations from two stakeholder meetings. See

http://www.ieep.eu/projectminisites/meacap/index.php

During the first period of the project (April 2004 – March 2005), work commenced on work packages 1-6, and consisted mainly of initial research and laying the foundations for the subsequent periods. The management structure for the project was established, along with a detailed methodology. The project’s website was set up and a project leaflet produced to raise awareness of the research programme. A paper on the significance of the 2003 CAP reform (D4b ‘Recent evolution of the EU CAP: state of play and environmental potential’) was produced which was not anticipated as a deliverable, but provided a detailed analysis of recent changes against which any further changes to the CAP could be assessed. This report proved to be one of the first analyses of its kind and was helpful for the project team and informative for other related projects. The paper was distributed via the project website and emailed to the project mailing list.

A number of other deliverables were also finalised during this period including: D2 ‘Initial paper setting out implications of the CBD for the agricultural sector’; D3 ‘Initial report assessing Kyoto Protocol commitments for the EU’; D4a ‘Initial paper on the ground rules for WPs 3, 4 and 5’; D5 ‘Survey of GHG reduction policies and agricultural measures in EU and candidate countries’; and D7 ‘Report on survey of GHG mitigation options’.

During the second period of the project (April 2005 - March 2006), the majority of the work to identify and assess measures aimed at mitigation and bioenergy supply in the agriculture sector; at the forestry sector; and at enriching biodiversity in agriculture was carried out. Although Deliverables 3 and 5 were completed in the first period, in order to satisfy the overall objectives of WP2 in more depth, it was agreed to devote more work to D3 and D5 during the second and third year of MEACAP. As such, D3 and D5 were updated in this period. In addition, the following deliverables were completed: D6 ‘Economic evaluation of mitigation policies/technical measures in the agricultural and forestry sectors’; D10 ‘List of GHG mitigation potential, abatement costs and technical feasibility of mitigation options and production chains’; and the WP6 non-deliverable paper ‘Modelling approaches and other quantitative methods for policy analysis’.

In February 2005, a workshop for WP5 partners was held in Vilnius, Lithuania, to identify case study areas to explore three topics focusing on the new Member States: semi subsistence farming, arable production on large scale farms, and land abandonment.

In June 2005, a joint workshop for the biodiversity team (D8) (IEEP, FAL, HUB, SAC) was held in Nitra, Slovakia to address the case study work and the screening of technical measures to support biodiversity.

In September 2005, a meeting was held in Berlin with IEEP, IE, FAL, HUB/SAC and Alterra in order to clarify how to combine the outputs of work packages 3, 4 and 5 into WP6.

The first stakeholder meeting was organised in Brussels in March 2006 in order to present the preliminary results of the project to an audience for external review and critical feedback, and to facilitate a discussion about the policy interest and relevance of the work. The meeting included presentations from the individual work packages, with time for discussion and participant input.

During the third period of the project (April 2006 – June 2007), all work packages were completed. Deliverables 3, 5 and 6 were updated and the following deliverables were finalised: D11 ‘Quantification of carbon gains of selected technical and management-based mitigation measures in forestry’; D12 ‘Expected impact of the Kyoto Protocol on European forestry’; D13 ‘Survey of technical and management based mitigation measures in forestry’; D14 ‘Overview of the selection of biodiversity technical measures’; D15a ‘Greenhouse gas emissions and mitigation costs of selected mitigation measures in agricultural production’ and D15b ‘Greenhouse gas emissions and mitigation costs of selected bioenergy production chains’; D16a ‘Analysis of policy instruments for greenhouse gas abatement and compliance with the Convention on Biodiversity’ and D16b ‘Market impact analysis of biofuel policy implementation’; D17 ‘The implementation of the Kyoto Protocol: Current state and implications for agriculture and forestry’; D19 ‘Modelling Approaches and other Quantitative Methods for Policy Analysis’.

MEACAP's final stakeholder meeting on 'A New Climate in the CAP?' was held on 13 March 2007 at Scotland House, Brussels. The meeting was attended by Commission and national officials and people from NGOs. It aimed to present the final research findings to an external audience for feedback, to discuss its policy implications, and to bring together people working on a similar range of issues to develop thinking in this area. The meeting involved presentations of the results of each work package and participants were invited to provide feedback on a draft version of the MEACAP strategy (D20). The feedback obtained from this meeting was used to develop the final version of the strategy (D21). The presentations given at the meeting can be found on the MEACAP website.

The final project report (D21) takes the form of a strategy presenting the results of the MEACAP project over the three year period and draws on the deliverables of each work package to examine the obligations on the EU arising from the two multilateral agreements, the Kyoto Protocol and the CBD, and to consider their implications for the Common Agricultural Policy (the CAP).  The strategy proposes a number of measures for adapting the CAP in order to meet these two commitments.

# Dissemination and use

| Date and Location | Type | References | Nature of Contribution | Size of Audience | Partners Responsible |
| --- | --- | --- | --- | --- | --- |
| Ongoing | Website | http://www.ieep.eu/projectminisites/meacap/ The project website is the key method of disseminating the project’s results. All papers produced for the project can be downloaded as well as presentations from the two stakeholder events. |  | Unknown | IEEP |
| 27-29 September 2004 | 44th annual meeting of the Gesellschaft fur Wirtschafts-und Sozialwissenschaften des Landbaus e.V.: Environmental and Product Quality in Agriculture |  | Poster presentation | 250 | HUB |
| 11 October 2004 | Workshop |  | GHG mitigation options in agricultural production: list of possible GHG measures | 12 | IE |
| 14 October 2004 | ‘Wird die Agrapolitick’ | Published in HUMBO LDT, Jg. 49, 14 Oct 2004, p10. | Press article |  | HUB |
| 9 December 2004 | Workshop |  | Biomass production and provision chains and conversion technologies: pre-selection of relevant bioenergy conversion technologies | 10 | IE |
| 24-28 January 2005 | International conference ‘Biodiversity: Science and Governance’ |  | Poster presentation | 50 | HUB |
| 19 May 2005 London, UK | LUPG Strategy Meeting |  | Presentation on future policy in Europe, insights from MEACAP | 20 Countryside Statutory agencies and policymakers | IEEP |
| 20 May 2005 Berlin, Germany | Ernährungsdienst: Bioenergy - Chance or ‘hot air’? |  | Participation, information gathering | 100 | FAL |
| 26 – 28 May 2005 Tartu, Estonia | International conference on multifunctional land use | http://www.sfb299.de/conference/programme.htm | Participation and presentation of poster, information gathering | 100 | FAL |
| 30 – 31 May 2005 Berlin, Germany | DLG and WWF colloquium: Energy from biomass - challenge for agriculture and nature conservation |  | Participation, information gathering | 60 | FAL |
| August 2005, Brussels | Helping WWF Reach a Common Position on Biofuels |  | Presentation | 10 Policy-makers, NGOs | IEEP |
| 24-27 August 2005 Royal Veterinary and Agricultural University, Copenhagen, Denmark | XIth International Congress of the European Agricultural Economists: ‘the future of rural Europe in the global agri-food system.’ | http://www.eaae005.dk | Submission of poster proposal | 537 Scientific audience | HUB |
| September 2005 Southampton, UK | Biomass Trees for Bioenergy: Stakeholder Meeting |  | Presentation | 27 | IEEP |
| September 2005 ISPRA, Milan, Italy | Joint Research Council seminar of Pillar 1 CAP & the Environment |  | Presentation on modelling AE policy interactions; exchange with managers of modelling projects | 40 Policy-makers, modellers, EEA, Commission officials. | IEEP |
| 5 - 7 October 2005 | 45th annual meeting of the Gesellschaft für Wirtschafts- und Sozialwissenschaften des Landbaus e.V. (GeWiSoLa): „Unternehmen im Agrarbereich vor neuen Herausforderungen“ (Agricultural businesses confronted with new challenges) | http://www.uni-goettingen.de/de/sh/21679.html | National Conference | 230 | HUB |
| 6 October 2005 Göttingen, Germany | Tagung der Gesellschaft für Wirtschafts- und Sozialwissenschaften des Landbaues (GEWISOLA) | http://www.uni-goettingen.de/de/sh/22632.html | Presentation of paper | 150 | FAL |
| 20 October 2005 | Summary of D13 into a chapter of the IPPC fourth Assessment report |  | IPCC Fourth Assessment Report | Scientific and policy community | Alterra |
| 26 – 27 October 2005 Norway | Nordic Bio-energy Conference |  | Presentation of Bioenergy study in collaboration with EEA bioenergy study | Scientific audience, policy-maker and entrepreneurs | EFI |
| 13. December 2005 Humboldt University, Germany | Research colloquium at HUB, Department of Agricultural Economics and Social Sciences, Division of Resource Economics |  | Internal | ~15 | HUB |
| 17 January 2006 IGW, Berlin, Germany | Fachagentur Nachwachsende Rohstoffe, Conference on biofuels. |  | Participation; information gathering | 130 | FAL |
| 19 January 2006 IGW, Berlin, Germany | Deutscher Bauernverband, Conference on bioenergy. |  | Participation; information gathering | 500 | FAL |
| 30 - 31 January 2006 | End-Symposium of EU 5th framework project EASY (on evaluation of AES) | www.easy2006.bureaupost.nl/ | Presentation of poster on research within MEACAP about delivering CBD commitments | 150 | FAL |
| 31 January 2006 DG Environment, Brussels | 1st meeting on European Climate Change Programme review, agriculture. |  | Presentation on preliminary results of MEACAP; information gathering | 60 | FAL |
| 31 January 2006 | Working group ECCP I review, Topic group ‘agriculture and forestry’ | http://forum.europa.eu.int/Public/irc/env/eccp_2/library?l=/eccp_agriculture&vm=detailed&sb=Title | Meeting | 60 key international experts, stakeholders from Member States, NGOs, academia and industry | FEEM |
| 2 March 2006 DG Environment, Brussels | 2nd meeting on European Climate Change Programme review, agriculture |  | Participation; information gathering | 80 | FAL |
| 13 March 2006, Brussels | Stakeholder consultation meeting | http://www.ieep.eu/projectminisites/meacap/stakeholder_events.php | Dedicated day on MEACAP for Commission | c.25 commission and national officials and other stakeholders | All partners |
| 30 April 2006 | A literature survey on the cost effectiveness of GHG mitigation measures in the agro-forestry sector | http://www.elsevier.com/wps/find/journaldescription.cws_home/601264/description#description | Journal submission | Experts from government, business, industry, academia, and non-governmental organisations. | FEEM |
| 10 May 2006 London, UK | Pesticides Action Network meeting |  | Participated in meeting |  | IEEP |
| 17 May 2006 London, UK | Green Alliance Spring reception – focus on climate change |  | Panellist |  | IEEP |
| 18 - 19 May 2005 Gießen, Germany | International conference "Multifunctionality of Landscapes" | http://www.sfb299.de/conference/ | Participation and presentation of poster, information gathering | 100 | FAL & HUB |
| 19 May 2006 French embassy, London | Meeting with French agricultural experts. |  | Discussed implementation of 2003 CAP reform and Natura 2000 in France and the UK | 10 | IEEP |
| 24 May 2006 London, UK | Launch of All Party Parliamentary Environment Group report on the Government’s climate change programme |  | Author of report and presented report at launch meeting |  | IEEP |
| 20-21 June 2006, Turkey | Developing agri-environment programmes in Turkey |  | Presentation | 50 | IEEP |
| 11 July 2006, DG Agriculture, Brussels | Expert meeting on assessing the effects of rural development policy |  | Participated in meeting |  | IEEP |
| 22 September 2006, Brussels | EEB Conference ‘Can the EU strengthen its leadership in environment protection?’ |  | Panellist for discussion on the 6th EAP review | 45 | IEEP |
| 06 October 2006 Copenhagen, Denmark | Seminar on Natura 2000 |  | Participant in expert group |  | IEEP |
| 13-14 October 2006 Turkey | Meeting on agri-environment and HNV farming |  | Presentation | 25 | IEEP |
| 24 October 2006, Vilnius, Lithuania | MCPFE Workshop on pan-European recommendations for afforestation and reforestation in the context of UNFCCC |  | Quantitative overview and analysis of afforestation in Europe |  | EFI |
| 8 November 2006 Luckenwalde, Germany | Berlin-Brandenburgisches Forschungssymposium 'Stoffliche und energetische Verwertung nachwachsender Rohstoffe - neue Produkte und Technologien' |  | Presentation 'Aktuelle Aspekte der Züchtung und Fruchtfolge bei nachwachsenden Rohstoffen' | Approx. 80 researchers at Forschungs-institut Biopol, Biotechnologie-park Luckenwalde | IE |
| 16 November 2006, Florence Italy | Conference, Sustainable Rural Development: Applied Science for Knowledge Driven Governance conference | http://www.economia.unifi.it/upload/sub/80Anni/englishbrochure.pdf | Key-note speaker and presentation | 150 | IEEP |
| 20 November, Imperial College London’s Wye Campus | Workshop: Agricultural Trade and Policy Reform: Where is the Action? Including an item on The Next Stages in the Reform of the CAP |  | Key-note speaker and presentation |  | IEEP |
| 5 December 2006 Dessau, Germany | 'Bodenschutz und nachwachsende Rohstoffe' |  | Poster 'Greenhouse gas mitigation in European farming systems' | Approx. 250 researchers and stakeholders at Umweltbundesamt, Dessau | IE |
| 07-08 December 2006 Warsaw, Poland | International seminar on ‘the relationship between the CAP and biodiversity’ |  | Delivered background paper and acted as rapporteur at the seminar | Approx. 100 | IEEP |
| January 2007 | Input to EEA report: Environmentally compatible bio-energy potential from European forests | Report available at http://biodiversity-chm.eea.europa.eu/information/database/forests/EEA_Bio_Energy_10-01-2007_low.pdf | Input to EEA report by M. Lindner, J. Eggers, G. Zanchi, A. Moiseyev, K. Tröltzsch and T. Eggers |  | Alterra |
| January 2007 | FEEM Working Paper: ‘The Kyoto Protocol and the effect of existing and planned measures in the agricultural and forestry sector in the EU25’. | Bosello, F., B. Buchner, J. Crimi, C. Giupponi, and A. Povellato. FEEM Working paper n. 13.07 | Working paper |  | FEEM |
| January 2007 | FEEM Working Paper: ‘A review of recent studies on cost effectiveness of GHG mitigation measures in the European agro-forestry sector.’ | Bosello, F., C. Giupponi, and A. Povellato. FEEM Working paper n. 14.07 | Working paper |  | FEEM |
| March 2007 | EFI Technical Report: ‘Forest area change and afforestation in Europe: Critical analysis of available data and the relevance for international environmental policies.’ | G. Zanchi, D. Thiel, T. Green, M. Lindner. EFI Technical Report 24 | Technical report |  | EFI |
| 1 March 2007 Velp, The Netherlands |  |  | Lecture “Forests and carbon”, Hogeschool Larenstein (BSc level course) |  | Alterra |
| 13 March 2007 Brussels | A New Climate in the CAP, A Stakeholder Conference |  | Presentation of MEACAP results and draft strategy to stakeholders | Approx. 80 researchers and stakeholders at Scotland House, Brussels | All partners |
| 10 April 2007 Driebergen, the Netherlands | Climate objectives in State Forest Service Policy |  | Presentation “Forests and carbon” | 15 | Alterra |
| 23 April 2007, Bonn-Bad Godesberg, Germany | Nature Conservation, Agriculture and Rural Development – Where is the EU Headed? |  | Panel discussant |  | IEEP |
| 16 May 07, London UK | Green Alliance – Can Europe Lead the World to a Stable Climate? |  | Presentation and panel discussant |  | IEEP |
| 22 May 2007 London, UK | LUPG expert workshop to review four papers for conference ‘Future policies for rural Europe 2013 and beyond – delivering sustainable rural land management in a changing Europe’ |  | Presented paper ‘Climate change and the rural environment in a European context: implications for land use and land use policy’ | 15 experts | IEEP |
| 30 May 2007 London, UK | Meeting with Woodland Policy Group |  | Presentation on HNV forestry and biodiversity conservation | 4 | IEEP |
| 12 June 2007 Peterborough, UK | Joint Nature Conservancy Council (JNCC) meeting |  | Presentation on HNV farming | 20 | IEEP |
| June 2007 | Report: ‘Selection and quantification of forestry measures targeted at the Kyoto Protocol and the Convention on Biodiversity’ |  | M.J. Schelhaas, E. Cienciala, M. Lindner, G.J. Nabuurs, G. Zianchi. Alterra report 1508. | Report | Alterra |
| June 26, Brussels | Natural England Adapt for Life event: Europe’s Natural Environment and the Climate Change Challenge |  | Facilitator of the debate |  | IEEP |
| 28-29 June 2007, Brussels | Assessing the Environmental Consequences of major CAP changes EEAC WG Agri-seminar. |  | Presentations |  | Alterra |
| 2007 in press | Journal article: ‘Cost-effectiveness of greenhouse gas mitigation measures in the European agro-forestry sector: a literature survey | Povellato, A., Bosello, F. and Giupponi, C., 2007. Cost-effectiveness of greenhouse gases mitigation measures in the European agro-forestry sector: a literature survey. Environmental Science and Policy. In press. | Journal article |  | FEEM |
| July 2007 | IEEP event on climate change |  | Active involvement in climate change discussions, presented research findings |  | IEEP |
| August 2007 | In focus: biodiversity and the CAP. - SAC Agribusiness News Volume 2, Issue 10, pages 13-14 | McCracken, D.I., | Article |  | HUB/SAC, FAL, IEEP |
| 2007 in press | Climate change and the rural environment in a European context: implications for land use and land use policy | Cooper, T. and Arblaster, K. | Background paper for LUPG conference on ‘Future polices for rural Europe 2013 and beyond – delivering sustainable rural land management in a changing Europe’ to be held in Brussels on 19-20 September 2007 |  | IEEP |
| 2007 |  | Osterburg, B, Nitsch, H, Gay, S H (2007); Landscape issues of the EU Common Agricultural Policy reform: implications for modelling. | Book article in Mander, Ü, Wiggering, H, Helming, K (ed.), Multifunctional Land use. Springer. pp 269-279. |  | FAL |