Project no.-  INCO- CT-2003-510363

Project acronym- NENAMAT

Project title- Network for nanostructured materials of ACC

Instrument - SSA

Thematic Priority- Nanotechnologies and nanosciences, knowledge-based multi-functional materials and new production processes and devices

PUBLISHABLE FINAL ACTIVITY REPORT

Period covered: from  01/08/2004  to 31/07/2006

Date of preparation: 10/10//2006

Start date of project:	01/08/2004				Duration: 2 years

Project coordinator name – Prof. Dr. Jan Dusza, DrSc.         Revision - draft 1

Project coordinator organization name – Institute of Materials Research,

Slovak Academy of Sciences, Slovakia

1. Project execution

The main objective of the project is to mobilize human and material resources in the field of nano-structured materials in ACC, to consolidate, strengthen, and enhance the dispersed research/technological potential in this field of research, to promote and exploitate results of 5thFP and 6thFP, and to improve the knowledge based application oriented nanoscience and technology in Europe.

The further objective is to improve significantly the communication and collaboration between the Centers working in this area of research in individual ACC, between the Centers in ACC, Member State Countries, Russia NIS and SEEC which will contribute to the building and strenghtening of ERA. To fulfill this objective an effective system for information exchange and system for training/mobility will be established.

An important objective is to disseminate scientific information as well as the results of research and development and to create a common platform for coordinate research, education, and training activities in ACC in the field of nano-structured materials and nanoscience/technology.

A very important objective is to integrate the ACC activities to ERA and contribute to the development of radical breakthrough production technologies leading to the mass production of nanopowders and nanocomponents of high quality or self-controlled manufacturing operations.

The specific objectives of the NENAMAT are:

- sharing and developing research infrastructure of the Network partners

- monitoring common interest and generating interdisciplinary research projects

- planing the research activities to avoid duplicate research

- to improve the position of female in research

- to improve the protection of intellectual knowledge

- to improve education in the nanoscience/technology and related fields

- to help in creation of „knowledge communities“ in nanotechnologies

- to elaborate technological roadmaps in nanosciences and nanotechnologies

- to integrate education and skills development with the research activities

The Contractors involved

- Institute of Electrochemistry and Energy Systems of the Bulgarian Academy of Sciences, Sofia, Bulgaria

- Faculty of Mechanical Engineering of the Brno University of Technology, Brno, Czech Republic

- Institute of Materials Technology, Tallin Technical University, Tallin, Estonia

- Research Institute for Technical Physics and Materials Science of the Hungarian Academy of Sciences, Budapest, Hungary

- Institute of Inorganic Chemistry of the Riga Technical University, Riga, Latvia

# Faculty of Materials Science and Engineering, Warsaw University of Technology, Warszaw, Poland

- National Institute of Research and Development for Technical Physics Rumania

- “Jožef Stefan” Institute, Department of Engineering Ceramics, University of Ljubljana, Ljubljana, Slovenia

- Isik University, Maslaki, Istambul, Turkey

The coordinator of the project:

Institute of Materials Research of the Slovak Academy of Sciences, Košice, Slovak Republic

Co-ordinator name:			Ján Dusza

Co-ordinator organization name:  Centre of Nanostructured Materials of the Slovak Academy of Sciences, Institute of Materials Research, SAS

Co-ordinator E-mail:			dusza@imrnov.saske.sk

Co-ordinator fax:			+421-55-7922-408

The realized work during the Project was connected with the following activities/ work packages:

Kick-off meeting

SWP1:  National “Mobilization workshops”

SWP2:  Information&communication tools

SWP3:  Sharing and Development of the Infrastructure

SWP4: Expert Council & Working Groups

SWP5: Training and Mobility of young researchers

SWP6: Workshop and Conference

Kick-off meeting 19. – 20.10.2004, Institute of Materials Research, SAS,Watsonova 47, 043 53 Košice, Slovakia

SWP1:  National “Mobilization workshops”

Term:		between the 3rd and 8th month

Goals:		To mobilize the human and material resources in the field of nanomaterials and technology in ACC; to contact key partners and their RTD potential & capabilities, to discuss advanced initiatives, methods, techniques and new strategies.

Leaders: 	National Coordinators

Deliverables:	Series of 10 Workshops, Book of Abstracts

The Mobilization workshops in the individual NENAMAT countries have been realized between October 2004 – Czech Republic and  July, 2005, -Turkey. The only exception was Slovenia where there was no need to organize a special mobilization workshop immediately after the 4th SLO-NANO meeting held in September 2004 in Ljubljana. Instead, in agreement with the NENAMAT project coordinator and the EC project officer a summary report including main research activities and human and material resources in the field of nanomaterials and nanotechnologies in Slovenia was prepared. In June 2005 a thematic Symposium on Inorganic Nanomaterials was organized in Portoroz, Slovenia, as part of the IXth Conference & Exhibition of the European Ceramic Society with active participation of leading scientists in this field from Slovenia, who were invited to present their activities to the European scientific community.

The goals of the WP have been reached. There were mobilize the human and material resources in the field of nanomaterials and technology in individual NENAMAT countries the key partners have been contacted and their RTD potential & capabilities have been mapped. Advanced initiatives, methods, techniques and new strategies have been discussed between the research groups in the individual countries.

SWP2:  Information&communication tools

Term:		between 1st and 24th month

Goals:	Integration of NENAMAT activities through NENAMAT internet, developing a promotion and dissemination tool to support the NENAMAT activities

Leader:	Prof. Horia Chiriac

T  2-1:		Development of a NENAMAT Intranet

Term:		from 1st to 10th month

Objectives:   – to develop an Intranet communication system with the aim to integrate NENAMAT activities

– to use the developed Intranet as a communication and management tool

Deliverables:	Intranet system

T  2-2:		Development – Maintaining -  Update of the NENAMAT web page

Term:		from 1st to 24th month

Objectives:	to develop, maintain, and update the NENAMAT web page containing activities of the network and related information

Deliverables:	NENAMAT web page

The NENAMAT Project webpage was designed by NIRDTP Iasi contractor and made available at the following 2 addresses: http://www.phys-iasi.ro/NENAMAT.nenamat.html and http://www.NENAMAT.phys-iasi.ro, on April 8, 2005. Since then, the webpage was updated regularly, when new information became available from other partners.

A forum of discussions has been linked to the NENAMAT webpage and it is accessible (will remain like that for at least one year from the ending date of the project) to all project partners (each contractor responsible and his/her deputy) with the following username and password:

Username: nenamat

Password: project

Any other users which want to access the forum webpage could login by creating their own username, and the password will be generated automatically. The idea was to follow and have full control over the potential users, due to security reasons and because the project webpage is located on the NIRDTP Iasi web server. This secured webpage might also contain the financial information, forms and management tasks of the project (after the project ending date), if the project partners will decide so.

SWP3:  Sharing and Development of the Infrastructure

Term:		from 1st to 24th month

Goals:	– to prepare a catalogue of the research infrastructure, equipment,    methods available at each Institute in the ACC

– to prepare a system of access to the NENAMAT infrastructure.

Leader:	Prof. Tadeusz Kulik

T 3-1:	Maping of the Infrastructure

Term:		from 1st to 24th month

Objectives:	to prepare a portfolio of infrastructure, equipment and methodology available at the NENAMAT Institutes;

to prepare and update a catalogue;

Deliverables:	catalogue of the infrastructure, equipment, and methodology report of the specialization and complementary of the infrastructure

The preliminary agreements with the NENAMAT website administrator were made on the location and linking of the database to the main website. Finally, it was decided that the website would be set up on the server of the Faculty of Materials Science and Engineering, WUT, and there will be the link to the database from the NENAMAT website. Since there were too few responses to the questionnaires that had been disseminated, it was decided that the information in the database will be limited to the basic info on the equipment, and this finally was the successful solution. The new questionnaires were disseminated, and the database admin received the responses. The final shape of the database and the search engine interface were established. The subcontractor for the database creation and launching was selected and performed the task. The input from the NENEMAT members was included in the database. The access to the database is restricted to the network members, and is secured with the login name and password. The logins and passwords were disseminated to National Coordinators and further to other members of the network.

The information concerning the infrastructure existing in the other R&D institutions being active in the Nanomaterials development in Nenamat countries have been submitted to WUT Warsaw for the project infrastructure database. The database is located on Polish Partner web-server, and a link to the NENAMAT webpage was created, too.

SWP4: Expert Council & Working Groups

Term:		from 1st to 24th month

Goals:	to create an Expert Council and Working Groups from the leading international experts of ACC with the aim to transfer the results of the supporting activities into the scientific/research/application field in different areas of nanoscience and nanotechnology; to prepare studies, analysis concerning the State of the Art of research and development in individual areas of nanoscience & nanotechnology; to define the scientific program of Summer Schools, Workshops and Conference, to initiate new co-operations, joint projects, introduction of new concepts, methods/techniques.

Leaders:	Prof. T. Kosmač, Prof. J.Švejcar

TS 4-1:	Organization of an International Expert Council & Working Groups of ACC

Term:		from 1st to 5th month

TS 4-2:	Structuring of thematic priorities

TS 4-2-1:	Nanopowders/Nanoparticles

TS 4-2-2:	Nanostructured Metallic Materials

TS 4-2-3: 	Nanostructured Ceramic Materials

TS 4-2-4:	Thin films, Dots, and Multilayered Nanosystems

TS 4-2-5:	Nanotubes, Nanowires & Self Organization Phenomena

TS 4-2-6: 	Nanometrology, Non–metallic and Non–ceramic nanomaterials

Deliverables: Studies, Reports, new methods/techniques

Responsible Coordinators (Prof. Švejcar, and Prof. Kosmac) worked to establish the Expert Council & Working Groups via e-mail and phone communication. Within the Summer School in Primorsk a meeting was held, with the participation of both coordinators and some members of EC and WG, who lectured in the Summer School. In compliance with the project proposal, six working groups were formed, which for practical reasons (flexible communication with coordinators) are headed by leading workers from the CR and Slovenia.

There were 3 Expert Council & Working Groups meetings which were connected with the NENAMAT Summer School in Bulgary, NENAMAT Workshop in Brno, Czech Republic and with the NENAMAT Conference in Stara Lesna, Slovakia. The first meeting was orientated mainly to the preparation of the NENAMAT Workshop the second the NENAMAT Conference and the third mainly to the future, how to arrange the future collaboration of the NENAMAT participants.

Studies and  reports have been prepared by the  members of Expert Council & Working Groups concerning the new areas and results  of research and new  methods/techniques in the nano-materials research. These were presented at the NENAMAT or other meetings  and/or published as a review papers or chapters and are/will be available for the training of young researchers and PhD students in this field. Such a materials are for example:

Šajgalík, P., Dusza,J.,et. al :

Bulk Ceramic Nanostructures

I.Škorvánek:

„Magnetic Nanomaterials“, Summer School: "Advanced Nanotechnologies, Testing, Production and Application of Nanoscale Materials ", Primorsko, Bulgaria, 1.- 7. 6. 2005

Škorvánek, J. et al:,

Improved soft magnetic behaviour in field-annealed nanocrystalline Hitperm alloys, Journal

of Magnetism and Magnetic Materials 304 (2006) 203-207

Balaz, P.:

Mechanochemistry of sulphides: from minerals to advanced nanocrystalline materials, Vth Int. Conf. On Mechanochemistry and Mechanical Alloying, INCOME 2006, Novosibirsk

Balazsi, Cs.:

Carbon nanotube-ceramic matrices: silicon nitride composites, Primorsko, Bulgaria, 1.- 7. 6. 2005

SWP5: Training and Mobility of young researchers

Term:	from 3rd to 24th month

Goals:	to prepare a plan for the training and mobility of young researchers under 35 years and to organize summer schools and exchange of researchers

Leader:	Prof.I. Dragieva, Assoc.Prof. J.Dusza

T5–1:	Training and Mobility Plan

Term:	from 3rd to 6th month

Objective:	Preparation of a plan for organizing Summer Schools and exchange of young researchers

###### Deliverables:	Action plan for training and mobility

T5–2:	Summer School. – „Advanced Nanotechnologies, Testing, Production and Application of Nanoscale Materials “

with approx. 15-20 students/PhD students from ACC and approx. 3-5 invited lecturers from Member States.

Term:	from 8th to 11th month; Place: Bulgaria

Objective:	Education and training of young researchers

Deliverables:	Book of lectures

The Summer School: "Advanced Nanotechnologies, Testing, Production and Application of Nanoscale Materials" was organized jointly by the Institute of Electrochemistry and Energy Systems of the Bulgarian Academy of Sciences (Prof. Iovka Dragieva) and by the Research Institute for Technical Physics and Materials Science of the Hungarian Academy of Sciences (Dr. László P. Biró) 1st to 8th June, 2005 in Primorsko, Bulgaria..

PARTICIPANTS OF NENAMAT – SUMMER SCHOOL

| Ani Proykova | Bulgaria Assoc. Prof. |
| --- | --- |
| Dessislava Kostadinova | Bulgaria PhD |
| Emilia Balabanova | Bulgaria Assoc. Prof. |
| Iovka Dragieva | Bulgaria Prof. |
| Kremena Aleksandrova | Bulgaria PhD |
| Nikola Stoichev | Bulgaria Assoc. Prof. |
| Tamara Pencheva | Bulgaria Assoc. Prof. |
| Vania Markova | Bulgaria Assoc. Prof. |
| Krassimira Angelova | Bulgaria Assoc. Prof. |
| Milen Nenkov Dr Penka Voneva PhD Jana Machackova | Czech Republic PhD |
| Jiri SVEJCAR | Czech Republic Prof. |
| Jozef Lukac | Czech Republic PhD |
| Pavla Roupcova | Czech Republic PhD |
| Petra Cihlarova | Czech Republic PhD |
| Prof. Pavel Lukac | Czech Republic Prof. |
| Simona Pospisilova | Czech Republic PhD |
| Lauri Kollo | Estonia PhD |
| Valterr Reedo | Estonia PhD |
| Andras Gergely | Hungary PhD |
| Csaba Balazsi | Hungary Dr |
| Dora Aranyi | Hungary PhD |
| Dr. L.P. Biro | Hungary Prof.. |
| G.I. Mark | Hungary Prof. |
| Robert Grasin | Hungary PhD |
| Tamas Gabor | Hungary PhD |
| Anatoly Sharakovsky | Latvia PhD |
| Krisjanis Smits | Latvia PhD |
| Bogusława Adamczyk-Cieślak | Poland PhD |
| Dr. Jarosław Jakubowicz | Poland Dr. |
| Grzegorz Cieślak | Poland PhD |
| Karol Kuczynski | Poland PhD |
| Prof. Mieczysław Jurczyk | Poland Prof.. |
| Adina Morozan | Romania PhD |
| Alexandra Vysocka | Slovakia PhD |
| Dr. Ivan Skorvanek | Slovakia Prof. |
| Prof.Dr. Jan Dusza | Slovakia Prof. |
| Jana Spakova | Slovakia PhD |
| A.Dakskobler | Slovenia Dr |
| Sabina Beraniĉ | Slovenia PhD |
| Tea Toplisek | Slovenia PhD |
| Tomaz Kosmac | Slovenia Prof. |
| V. Dimitrov | Turkey Prof. |

Special Programme for young researchers

European Commission  - Research Directorate – General 2003

- NANO : The next dimension ( 27 min documentary)

- NANOTECHNOLOGY: ( 29 min documentary )

State Univ. of Sofia, Bulgaria , Phil. Depart.( Dr. K. Angelova)

Written and oral presentation of scientific and research results

- Publishing for young scientists and researchers

- Strategies for information retrieval of specialized information

A contest for best poster was organized and 3 young authors (from the Czech Republic, Estonia and Bulgaria) were awarded and they made their first oral presentations on the following day. Two documentaries of the EC were shown and created great interest.

SWP6: Workshop and Conference

Term:	from 3th to 22th month

Goals:	to organize workshops and an international conference on nanomaterials with invited scientists from the Member States

Leaders:	Prof.J.Dusza, Dr. L.P.Biró

T6–1:	Plan of Workshops and Conference

Term:	from 3rd to 6th month

Objective:	to prepare the plan and organization structure of two workshops and a conference

###### Deliverables:	Report – Plan

T6–2:	Workshop

Term:	from 15th to 18th month; Place:  Czech Republic

Objective:	to organize a workshop on „Nanostructured Materials for Functional ,Structural and Bio-Medical Applications“

with approx. 30 participants and invited lecturers from Member States

Deliverables:	Book of abstracts of the Workshop

On November 8 – 10, 2005, the NANO’05 – Nanostructured Materials for Functional, Structural and Biomedical Application” took place. In the project proposal this action was thought of as a workshop for approximately 30 participants and invited lecturers from Member States. Thanks to the extraordinary success of the National “Mobilization Workshop” held under the title NANO’04  (October 13-15, 2004), and also thanks to the active approach of the members of Czech core group, this action could, because of its extent, no longer be considered a workshop (hence the name Conference).

## Overview of the invited lectures

- Carbon Nanotube - Ceramic Composites, Csaba Balázsi, Research Institute for Technical Physics and Materials Science, Hungary

- Novel Carbon Nanotube Type Nanoarchitectures , László Bíró, MFA Research Institute for Technical Physics and Materials Science, Budapest, Hungary

- The Art of Chemical Bond Creation in Nanonoscale Materials, Iovka Dragieva, Bulgarian Academy of Sciences,Sofia, Bulgaria

- Analytical Electron Microscopy in the Characterization of Nanostructured Materials: Where are the Practical Limits?, Goran Drazic,  Jožef Stefan Institute, Ljubljana, Slovenia

- Nanostructured Ceramics, Ján Dusza Head, Centre of Excellence, Institute of Materials Research of SAS Kosice, Slovakia

- Preparation and Properties of New C/C-SiC Composites for Braking Systems, Kristoffer Krnel, Tomaž Kosmač, Zmago Stadler, Institut Jožef Stefan, Ljubljana, Slovenija

- Magnesium-Based Nanocomposites, Pavel Lukáč, Zuzanka Trojanová, Matematicko-fyzikální fakulta Uk, Katedra fyziky kovů, Czech Republic

- Synthesis and Structural Properties of Spinel Ferrite, Darko Makovec, Aljoša Košak, Miha Drofenik, Iztok Arčon, Alojz Kodre, Advanced Materials Department, Jožef Stefan Institute, Slovenia

- Functionalized Nanowire-Based Field-Effect Transistors as Chemical and Biological Sensors, Martin Moskovits, University of California at Santa Barbara, Dept. of Chemistry and Biochemistry, USA

- Application of the New Method of Sample Controlled Reaction Temperature (SCRT) to the Synthesis and Processing of Nanostructured Materials, L. A. Pérez-Maqueda, Instituto de Ciencias de Materiales de Sevilla C.S.I.C., Spain

- Photocatalytic Technologies and Novel Nanosurfaces Materials in 2005, František Peterka,  Center for TiO2 Photocatalytic Applications, ATG Praha, Czech Republic

The Conference was held at the Faculty of Mech. Engineering, BUT Brno, CZ (the workplace of the national coordinator/contractor of the project, Prof. Švejcar, who was the guarantor of the Conference). A total of 68 read papers were presented (out of them 14 invited plenary lectures) in six sections and one workshop, the latter being focused on responsible approach to the nanotechnology research. Because of lack of time, another 42 papers were included in the poster section. More detailed information can still be had on the Conference web page (http://csnmt.fme.vutbr.cz/nano05). Thanks to the fact that considerable financial support could be obtained from the Czech Society for New Materials and Technologies) see also paragraph and other sponsors it was possible to hold the Conference on such a large scale and, among other things, to publish all the contributions both in the Book of Abstracts (paid for from the NENAMAT project) and also in full version in the Proceedings NANO’05. Invited lecturers were from among project joint researchers but also from the US (Prof. Moskovits), Russia (Prof. Goldstein), France (Prof. Špaňhel and Dr. Herlin-Boime) and Spain (Prof. Pérez-Maqueda). In an opinion poll the participants expressed their wish that these actions should continue so that  this year the Czech Core Group, under the leadership of the national coordinator

T6–3:	International Conference

Term:	from 21th to 22th month; Place: Slovak Republic

Objective:	to organize an international conference on „Advances in Nanostructured Materials,  Processing – Microstructure – Properties“

with approx. 75 participants and invited lecturers from Member States

Deliverables:	Book of abstracts of the Conference or special issue of „Nanomaterials“

The NANOVED 2006 – NENAMAT  International Conference , held on May 14-17, 2006 in Stara Lesna, Slovakia

This well prepared action was the “peak” of the NENAMAT activities which was comparing to the plan in the project proposal was significantly larger and more important.

As it was underlined by the Conference chairmen, Nanoscience and nanotechnologies are new approaches in research and development involving precise manipulation and control of atoms and molecules, applying nanoarchitectures, to create novel structures with unique properties. This influential technology requires detailed understanding of physical/chemical/medical processes, across a range of disciplines, at the scale of one billionth of a metre. The goal is to produce new materials, devices and systems’ tailored to meet the needs of a growing range of commercial, scientific, engineering and biomedical applications – opening new markets and giving dramatic benefits in product performance. These fields open up new possibilities of understanding new phenomena and creating advanced properties that can emerging and will impact on the life of every citizen. We may expect that in the next 50 years much stronger effects will be generated by nanotechnology. Therefore, it’s very important for all countries to be involved in the development of the nanotechnology and to have experts who may judge the positive effects and the risks of such a deep penetrating technology.

With the above aims have been initiated the 6th FP “Network for Nanostructured Materials of Asocciated Candidate Countries – NENAMAT “and the serie of conferences in Slovakia devoted to nanoscience and nanotechnology “NANOVED”. As they common action was organized in May 14-17, 2006 in the Hotel Academia, High Tatra region, Slovakia the International conference

“Advances in Nanostructured Materials – Processing, Microstructure, Properties”.

Scientists and PhD students from 13 Countries participated the Conference in total number of 170. Invited lectures (3), lectures (45) and posters (81) have been presented on the topics; Nanotubes, Nanowires, Nanopowders, Theoretical Problems, Education and Application, Metallic Nanostructured Materials, Ceramic Nanostructured Materials, Polymers and Nanostructured Biomaterials, Thin Films and Coatings, Characterization and Testing.

The presentation ( recently in press) will be published in the following scientific journals; Nanopages, Metallic Materials, Powder Metallurgy Progress and Acta Metallurgica Slovaca.

The Organizing committee would like to thank all members of the International Advisory Board for their assistance and valuable suggestion, the European Commission for the support of the Project NENAMAT, the effort of the authors in their precise preparation of the manuscripts and the referees for their contribution in improving the quality of the papers.

The participation wre from 13 countries: Bulgaria, Czech Republic, Estonia, Germany, Hungary, Israel, Latvia, Poland, Romania, Slovakia, Slovenia, Turkey, as follows;

Bulgaria

| Dragieva Iovka | Institute of Electrochemistry and Energy Systems, Bulgarian Academy of Science | oral |
| --- | --- | --- |
| Kostova Nina G. | Institute of Catalysis, Bulgarian Academy of Sciences | oral |
| Petkova Tamara | Institute of Electrochemistry and Energy Systems Bulgarian Academy of Sciences | oral |
| Petkov Plamen | Thin Films Technology Lab., Department of Physics University of Chemical Technology & Metallurgy |  |
| Roussev Dimitar | Thin Films Technology Lab., Department of Physics University of Chemical Technology & Metallurgy | oral |
| Markova-Deneva Ivanya | University of Chemical Technology and Metallurgy | poster |

Czech Republic

| Buksa Michal | Institute of Physics of Materials, AS CR |  |
| --- | --- | --- |
| Cihlářová Petra | Faculty of Mechanical Engineering Brno University of Technology | poster |
| Černický David | Struers GmbH, Organizační složka |  |
| David Bohumil | Institute of Physics of Materials, AS CR | poster |
| Drnek Jaroslav | COMTES FHT s.r.o. | oral |
| Filip Jan | Institute of Physics of Materials, AS CR | oral |
| Holoubek Jaroslav | Institute of Macromolecular Chemistry, AS CR | oral |
| Horníková Jana | Faculty of Mechanical Engineering Brno University of Technology | poster |
| Hrdý Radim | Department of Microelectronics Faculty of Electrical Engineering and Communication | poster |
| Kander Ladislav | Vítkovice – Research and Development, Ltd. | poster |
| Klosová Kateřina | Department of Microelectronics, Faculty of Electrical Engineering and Communication Brno University of Technology | poster |
| Kristofory František | Faculty of Mechanical Engineering, Department of mechanical technology Technical University of Ostrava | poster |
| Kučerová Zuzana | Faculty of Science, Department of Physical Electronics Masaryk University | poster |
| Lukáč Pavel | Faculty of Mathematics and Physics, Department of Metal Physics Charles University | oral |
| Mikuláš David | Faculty of Mechanical Engineering, Department of mechanical technology Technical University of Ostrava |  |
| Náhlik Ľuboš | Institute of Physics of Materials, AS CR | oral |
| Novoveska Katerina | CPN s.r.o. |  |
| Ostapchuk Tetyana | Institute of Physics, AS CR | oral |
| Roupcová Pavla | Institute of Physics of Materials, AS CR | poster |
| Rožek Zbigniew | Faculty of Mechanical Engineering, Department of materials science Technical University of Liberec |  |
| Rybka Radim | Oxford Instruments Analytical |  |
| Srbková Zuzana | JEOL (EUROPE) S.A. |  |
| Šandera Pavel | Faculty of Mechanical Engineering Brno University of Technology |  |
| Švejcar Jiří | Faculty of Mechanical Engineering Brno University of Technology | oral |
| Tůmová Štěpánka | Faculty of Mechanical Engineering, Department of materials science Technical University of Liberec |  |
| Vítů Tomáš | Faculty of Mechanical Engineering, Department of Applied Physics, CTU Prague | poster |
| Zrník Jozef | COMTES FHT s.r.o. | oral |

Estonia

| Krunks Malle | Department of Materials Science, Tallinn University of Technology | oral |
| --- | --- | --- |
| Mere Arvo | Department of Materials Science, Tallinn University of Technology | poster |

Germany

| Fritz Christian | Logitech |  |
| --- | --- | --- |
| Riedl Ralf | Institute of Materials Science, Darmstadt University of Technology | invited |
| Schmittgens Ralph | Institute for Solid State Electronics, Department of Electrical Engineering and Information Technology, Dresden University of Technology |  |

Hungary

| Balázsi Csaba | Research Institute for Technical Physics and Materials Science | oral, 2 x poster |
| --- | --- | --- |
| Biró Lászó Péter | Research Institute for Technical Physics and Materials Science | oral |
| Grasin Robert | Research Institute for Technical Physics and Materials Science | poster |
| Horváth Enikő | Research Institute for Technical Physics and Materials Science | poster |
| Horváth Zsolt E. | Research Institute for Technical Physics and Materials Science | oral |
| Kamarás Katalin | Research Institute for Solid State Physics and Optics. Hungarian Academy of Sciences | invited |
| Kerner Zsolt | Atomic Energy Research Institute |  |
| Kertész Krisztián | Research Institute for Technical Physics and Materials Science |  |
| Kiricsi Imre | Applied and Environmental Chemistry Department, University of Szeged | oral |
| Kónya Zoltán | Department of Applied and Environmental Chemistry University of Szeged | oral |
| Radnoczi Gyorgy | Research Institute for Technical Physics and Materials Science | oral |
| Sedlackova Katarina | Research Institute for Technical Physics and Materials Science | poster |
| Tóth Lajos | Research Institute for Technical Physics and Materials Science | oral |

Israel

| Stolyarova Sara | Solid State Institute and Microelectronics Research Center, Technion - Israel Institute of Technology | poster |
| --- | --- | --- |

Latvia

| Grabis Janis | Institute of Inorganic Chemistry, Riga Technical University | poster |
| --- | --- | --- |
| Kalinko Aleksandr | Institute of Solid State Physics, University of Latvia | poster |
| Muktepavela Faina | Institute of Solid State Physics, University of Latvia | poster |
| Orlov Alexander | Institute of Inorganic Chemistry, Riga Technical University | poster |
| Sakale Gita | Technical Physics Institute, Riga Technical University | poster |
| Smits Krisjanis | Institute of Solid State Physics, University of Latvia | poster |
| Zalite Ilmars | Institute of Inorganic Chemistry, Riga Technical University | poster |

Poland

| Antolak Anna | Faculty of Materials Science and Engineering, Warsaw University of Technology | poster |
| --- | --- | --- |
| Cieslak Grzegorz | Faculty of Materials Science and Engineering, Warsaw University of Technology | poster |
| Gramatyka Paweł | Institute of Engineering Materials and Biomaterials, Silesian University of Technology | poster |
| Kolano-Burian Aleksandra | Institute of Non-Ferrous Metals | poster |
| Kowalczyk Maciej | Faculty of Materials Science and Engineering, Warsaw University of Technology | poster |
| Koziel Tomasz | Faculty of Metals Engineering and Computer Science for Industry University of Science and Technology | poster |
| Kulik Tadeusz | Faculty of Materials Science and Engineering, Warsaw University of Technology |  |
| Leonowicz Marcin | Faculty of Materials Science and Engineering, Warsaw University of Technology |  |
| Mitura Stanislaw | Technical University of Lodz |  |
| Niespodziana Katarzyna | Institute of Materials Science and Engineering, Poznan University of Technology | poster |
| Olescak Dariusz | Faculty of Materials Science and Engineering, Warsaw University of Technology | oral |
| Salach Jacek | Institute of Metrology and Measurement Systems Warsaw University of Technology | poster |
| Sówka Ewa | Faculty of Materials Science and Engineering, Warsaw University of Technology | poster |
| Szewczyk Roman | Institute of Metrology and Measurement Systems Warsaw University of Technology | poster |
| Tulinski Maciej | Institute of Materials Science and Engineering, Poznan University of Technology | poster |
| Witkowski Artur | Faculty of Materials Science and Engineering, Warsaw University of Technology | poster |
| Nowak Marek | Institute of Materials Science and Engineering, Poznan University of Technology | poster |
| Okonska Izabela | Institute of Materials Science and Engineering, Poznan University of Technology | poster |

Romania

| Ababei Gabriel | National Institute of Research and Development for Technical Physics | poster |
| --- | --- | --- |
| Chiriac Horia | National Institute of Research and Development for Technical Physics |  |
| Lupu Nicoleta | National Institute of Research and Development for Technical Physics | oral |
| Urse Maria | National Institute of Research and Development for Technical Physics | poster |

Slovakia

| Baláž Peter | Institute of Geotechnics, SAS | oral |
| --- | --- | --- |
| Balog Martin | Institute of Materials and Machine Mechanics, SAS | oral |
| Balog Miroslav | Institute of Inorganic Chemistry, SAS | poster |
| Barák Imrich | Institute of Molecular Biology, SAS | oral |
| Besterci Michal | Institute of Materials Research, SAS | poster |
| Bodišová Katarína | Institute of Inorganic Chemistry, SAS | poster |
| Bruncková Helena | Institute of Materials Research, SAS | poster |
| Capek Ignác | Polymer Institute, SAS | oral |
| Ceniga Ladislav | Institute of Materials Research, SAS | poster |
| Csach Kornel | Institute of Experimental Physics, SAS | poster |
| Diko Pavel | Institute of Experimental Physics, SAS | oral |
| Donič Tibor | Faculty of Mechanical Engineering, University of Žilina Centre of Technological Plastometry | oral |
| Dorčáková Františka | Institute of Materials Research, SAS | poster |
| Držík Milan | International Laser Center |  |
| Ďurišin Juraj | Institute of Materials Research, SAS | poster |
| Ďurišinová Katarína | Institute of Materials Research, SAS |  |
| Dusza Ján | Institute of Materials Research, SAS | poster |
| Ferdinandy Milan | Institute of Materials Research, SAS | poster |
| Füzer Ján | Institute of Physics, Faculty of Sciences, P.J. Šafárik University |  |
| Galusek Dušan | VILA - Centre of Glass Research | oral |
| Godočíková Erika | Institute of Geotechnics, SAS | poster |
| Hegedűšová Lucia | Institute of Materials Research, SAS |  |
| Herchl František | Institute of Experimental Physics, SAS | poster |
| Hnatko Miroslav | Institute of Inorganic Chemistry, SAS | poster |
| Hric Ľubomír | Institute of Inorganic Chemistry, SAS |  |
| Janičkovič Dušan | Institute of Physics, SAS |  |
| Klingová Simona | Department of International Cooperation, SAS |  |
| Kollár Peter | Institute of Physics, Faculty of Sciences, P.J. Šafárik University | poster |
| Kováč Jozef | Institute of Experimental Physics, SAS |  |
| Kováč Pavol | Institute of Electrical Engineering, SAS | oral |
| Műllerova Denisa | Institute of Molecular Biology, SAS | poster |
| Křesťan Jan | Institute of Inorganic Chemistry, SAS | poster |
| Kupková Miriam | Institute of Materials Research, SAS | poster |
| Kvačkaj Tibor | Faculty of Metallurgy, Department of Metal Forming Technical University of Košice | poster |
| Lenčéš Zoltán | Institute of Inorganic Chemistry, SAS | oral |
| Lobotka Peter | Institute of Electrical Engineering, SAS | oral |
| Lojanova Štefania | Institute of Inorganic Chemistry, SAS | poster |
| Longauer Svätoboj | Faculty of Metallurgy Technical University of Košice | oral |
| Majchrák Peter | Institute of Electrical Engineering, SAS | poster |
| Martikán Milan | Faculty of Mechanical Engineering, University of Žilina Centre of Technological Plastometry |  |
| Mikolaj Daniel | Institute of Materials Research, SAS |  |
| Miškuf Jozef | Institute of Experimental Physics, SAS | poster |
| Mockovčiaková Annamária | Institute of Geotechnics, SAS | poster |
| Müller Dušan | Institute of Physics, SAS | poster |
| Nagy Juraj | Institute of Materials and Machine Mechanics, SAS | poster |
| Nižník Štefan | Faculty of Metallurgy, Technical University of Košice | poster |
| Olekšáková Denisa | Institute of Physics, Faculty of Sciences, P.J. Šafárik University | poster |
| Orolínová Mária | Institute of Materials Research, SAS |  |
| Orolínová Zuzana | Institute of Geotechnics, SAS |  |
| Paluga Marek | Institute of Physics, SAS | poster |
| Rudnayová Emőke | Institute of Materials Research, SAS |  |
| Sedlák Marián | Institute of Experimental Physics, SAS | oral |
| Šajgalík Pavol | Institute of Inorganic Chemistry, SAS |  |
| Škorvánek Ivan | Institute of Experimental Physics, SAS | oral |
| Špaková Jana | Institute of Materials Research, SAS | poster |
| Štulajterová Radoslava | Institute of Materials Research, SAS | poster |
| Švec Peter | Institute of Physics, SAS | oral |
| Turčanová Jana | Institute of Experimental Physics, SAS | poster |
| Vávra Ivo | Institute of Electrical Engineering, SAS | oral |
| Vysocká Alexandra | Institute of Materials Research, SAS | poster |
| Zeleňáková Adriana | Institute of Physics, Faculty of Sciences, P.J. Šafárik University | poster |
| Zmorayová Katarína | Institute of Experimental Physics, SAS |  |
| Zubrik Anton | Institute of Geotechnics, SAS | poster |
| Sedláček Jaroslav | Institute of Inorganic Chemistry, SAS |  |
| Milkovič Ondrej | Faculty of Metallurgy, Technical University of Košice |  |
| Šefčíková Martina | Institute of Experimental Physics, SAS |  |
| Parilák Ľudovít | Institute of Materials Research, SAS |  |
| Samuely Peter | Member of the Presidium SAS |  |

Slovenia

| Jančar Boštjan | Jozef Stefan Institute | oral |
| --- | --- | --- |
| Kocjan Andraž | Jozef Stefan Institute | poster |
| Krnel Kristoffer | Jozef Stefan Institute | poster |
| Pribošič Irena | Jozef Stefan Institute | oral |
| Toplisek Tea | Jozef Stefan Institute | poster |
| Jančar Boštjan | Jozef Stefan Institute | oral |

Turkey

| Aktaş Bekir | Gebze Institute of Technology | poster |
| --- | --- | --- |
| Dimitrov Ventsislav I. | Department of Physics, Işık University | oral |
| Öztürk Tugba | Physics Department, Faculty of Science and Arts, ISIK University | poster |
| Rameev Bulat Z. | Gebze Institute of Technology | poster |
| Tok Umut | Physics Department, Faculty of Science and Arts, ISIK University | poster |

UK

| Cardwell David | IRC in Superconductivity, University of Cambridge | invited |
| --- | --- | --- |

From the discussion during the conference it seems that for the participants of the NENAMAT action the most valuable was the creation of new links and professional friendships which are expected to produce significant benefits in the coming years. A further valuable achievement was the possibility offered by the network for young scientists to meet their colleagues form other countries and to establish professional links in an early phase of their carrier.

Participants of the International conference

“Advances in Nanostructured Materials – Processing, Microstructure, Properties”. May 14-17, 2006 in the Hotel Academia, High Tatra region, Slovakia

Achievements within the activities outside WPs

As already given in the Periodic Activity Report for the first period of project solution, the activities of the Czech Core group led to the establishment of two teams that operate independently of the NENAMAT project (although member of the project Core group participate in them) to the benefit of the development of nanosciences, nanomaterials and nanotechnologies in the CR, The formation of the Czech Nano-Team should be emphasized, which embraces mainly physics-oriented workplaces (at universities and in the Academy of Sciences). The activities of this group focus primarily on the theoretical aspects of the nano-area. The group is very active, above all in organizing workshops and summer schools of high-level standing. The other team has come into being associated to the Czech Society for New Materials and Technologies (CSNMT) and is rather oriented towards cooperating with SME’s. The activities of the CSNMT nano-section in particular have become intermingled with the activities of the Czech Core group to such a degree that it resulted in the above-mentioned financial and other support of the conference held within the SWP6 activities. This support also holds for future activities after the termination of the project (e.g. the NANO’06 International Conference).

During fall 2005 new collaboration topics were developed with the group of Prof. Al. Darabont, from the Babes-Bolyai University, Cluj, Romania in carrying out joint experiments concerning carbon nanostructure growth and their applications to gas sensing. The collaboration is foreseen to continue after the closure of the NENAMAT project.

The Second Latvian conference on nanotechnologies “Functional Materials and Nanotechnologies” (www.cfi.lu.lv , March 27.-28., 2006) should be mentioned as a result of the project and the logical continuation of the first Latvian conference ”Nanomaterials and nanotechnologies” (Mobilization workshop in Latvia) in 2005.

Apart from the National Mobilization Workshop, two other meetings were organised, in which several members of the Polish Core Group took part:

- joint meeting of the Nanomaterials Section, Committee of Materials Science, Polish Academy of Sciences (PAS) and Micro- and Nanotechnology Section, Committee of Machines Construction, PAS, and

- joint meeting of Nanomaterials Section, Committee of Materials Science, PAS, and Structural Materials Section, Committee of Civil Engineering, PAS.

During the NENAMAT International Conference Dragieva realized contacts with Dr. Frantisek Peterka, which has been invited speaker and is  COST540 “PHONASUM” Action Proposer. Now ( since 2006 ) Bulgaria is official included in this action and  is presented in the list of Management Committee members  of COST 540 from Dr. Evelina Slavcheva from the Institute of Electrochemistry and Energy Systems at Bulgaria Academy of Sciences (or the partner institution of NENAMAT from Bulgaria ).

One of the latest and one of an very important result of the NENAMAT activities with a probably strong impact on the scientific collaboration of 5 less favorite region in Slovakia, Hungary, Poland, Rumania and Ukraina is the creation of the

Carpathian Virtual Research and Innovation Centre

with an aim to  improve significantly the communication and collaboration between the research Institutions  in different countries of this Carpathian region in the field of research, education and innovation which will contribute to the strengthening of the industry and improving the life in these countries and will contribute to the building and strengthening of ERA.

Recently there is an INTERREG III project between the Slovak and Hungarian party for 18 month and during this period we would like to expand this collaboration to the other partners from the countries as Poland, Ukraina and Rumania.

| Planned/actual Dates | Type | Type of audience | Countries addressed | Size of audience | Partner responsible /involved |
| --- | --- | --- | --- | --- | --- |
| 10/9 | National Mobilization Workshops | Research | Estinia,Latvia, Poland, Czech, Slovakia, Hungary Rumania Bulgaria Turky | 25 - 70 | NENAMAT Contractors |
| 0/1 | Media briefing | General | Slovakia | - | Coordinator |
| 1/1 | International Conference | Research | NENAMAT + International | 170 | NENAMAT Partners |
| 1/1 | International Workshop | Research | NENAMAT + International | 150 | NENAMAT Partners |
| 1/1 | Summer School | Research | NENAMAT + International | 40 | NENAMAT Partners |
| 1/1 | Project web-site | Scientific/Public | International | - | Rumania |
| 1/1 | Infrastructure catalogue | Research | NENAMAT | - | Poland |
| 30/90 | Posters | Research | NENAMAT + International | 350 | NENAMAT Partners |
| 35/100 | Presentations | Research | NENAMAT + International | 350 | NENAMAT Partners |
| 0/5 | New project generation | Research & Innovation | NENAMAT + International | - | NENAMAT Partners |
| 0/8 | New partnerships | Research & Innovation | NENAMAT + International | - | NENAMAT Partners |
| 0/5 | Invited lectures on the NENAMAT activities | Research & Innovation | International | Cca. 500 | Coordinator |

2. Dissimination and use

Overview table

The coordinator was very active in the promotion of the NENAMAT activities at

national, European and international level. He presented the results of the NENAMAT project as an invited lecturer at 4 international conference/workshop during the period the last was the EUROINDIANET workshop organized in Porto, Portugal.

The NENAMAT activities have been strongly promoted at national (NIRDTP Iasi is participating in the Romanian Initiative in Nanoscience and Nanotechnologies) and European level (NIRDTP Iasi is partner in the FP6 Coordination Action Project IMPART - Improving the understanding of the impact of nanoparticles on human health and the environment (Contract No. NMP4-CT-2005-013968).

It was a good collaboration between the NENAMAT and similar Nano-orientated EU projects as  NanoSci – ERA, MINAEAST, NANOMAT. The Coordinator was invited to give a lecture on NENAMAT activities at NanoSci – ERA meting in Amsterdam, 2006.

The information materials (leaflet and plagat) were distributed to different scientific actions and organizations.

Kosice, October, 2006

Prof. RNDr. Jan Dusza, DrSc.,

Coordinator