Project no.TSA3-CT-2004-511043

CRONET-DAYS

Promoting and facilitating ERA-networking between European Contract Research Organisations (CRO)

Instrument: 	     Specific Support Action

Thematic Priority:  SUSTAINABLE DEVELOPMENT, GLOBAL CHANGE AND ECOSYSTEMS

Executive summary suitable for publication

Period covered from 1st September 2004 to 31st may 2005

Preparation date: 31-05-2005

Start date of project: 01/09/2004					Duration: 9 months

Organisation name of lead contractor for this deliverable :  SIREHNA

Author of the document: Jean-Paul Borleteau

# Executive summary suitable for publication

Summary and description of CRONET-DAYS project objectives:

The goal of the Specific Support Action CRONET-DAYS is to facilitate and enhance the meeting between the Contract Research Organisations of European Research Area in Surface Transport Area (road, rail, waterborne, intermodality). It aims at:

- enhancing the creation of RD and Innovation projects in ERA

- initiating european partnerships (FP6 Integrated Projects and Network of Excellence, Eureka, bi- or tri-national projects)

- increasing technology transfert and synergies inter-RTO (sharing and combining knowledge, know-how, software, hardware, facilities, human ressources)

- networking on common RD areas by enabling cross-fertilisation of ideas and capabilities between the different surface transport modes

Research and Technology Organisations (RTOs) are major actors of technology RD and innovation , but are too fragmented. Very few individual RTOs  or companies that can reasonably claim to respond to challenges in RD sector due to increasing complexity and interdisciplinarity critical mass. For this purpose, support from EC is needed to initiate the networking process, so to integrate RTOs efficiently in European Research Area.

Beneficials results are also expected to stimulate high tech and medium tech SMEs on specific niche technology through their participation in RTO network and partnership.

This objective will be achieved by organising a two-days “Surface Transport” RTO meeting in Nantes, on in April 2005, including 20 general presentations (several large FP6 projects, five technology platforms), as well as one to one technical and business meetings between RTOs.

All related information on www.sirehna.com .

Contractor involved in CRONET-DAYS project

SIREHNA						FR

Co-ordinator contact details

# SIREHNA

# Name: 		Jean-Pierre Le Goff

Address: 	1 rue de la Noë      BP 42105      FR-44321 NANTES

Phone: 		+33.2.51.86.02.86

Fax:		+33.2.40.74.17.36

E-mail: 	sirehna@sirehna.ec-nantes.fr

Website : www.sirehna.com

Work performed, results achieved

This overall objective was achieved by organising a two-days “Surface Transport” RTO meeting in Nantes, on 28-29 April 2005, including 20 general presentations (large FP6 projects, five technology platforms ERRAC, ERTRAC, WATERBORNE, ARTEMIS, H2 & FUEL CELLS , as well as one to one technical and business meetings (about 540 meetings). On www.sirehna.com, presentations of speakers and list of participants can be downloaded.

Main achievements are:

- Establishment of a technical/scientifical (T/S) organisation to design/specify and prepare the event, with six organisation meetings (14th oct, 14th dec, 13th January, 25th feb, 4th april, 27th april)

- a first pre-announcement of CRONET-DAYS issued and published on websites (CORDIS, EARTO, ANVAR, ASRC, ….)  at the end of October 2004

- speakers were identified and contacted: 5 technology platforms + 15 large EU projects + representatives of EU DG Research and DG TREN, of PREDIT, of French Ministery of Research, …

- CRONET-DAYS brochure was printed and mailed during during the first 2 weeks of february’05  (more than 1000 invitations were sent)

- Electronic documents (brochure, registration form, list of hotels) were available on www.sirehna.com

- Electronic documents were sent by e-mail (more than 3000 invitations)

- Active marketing and promotion of CRONET-DAYS by individual e-mails and by dedicated phone; in particular strong promotion towards New Member States in EU

- RTOs of New Member States have shown great interest in such an initiative and asked to be continuously informed about any future similar event.

- Collecting participant’s wishes and organising the scheduled ONE to ONE meetings

- Organising venue of the event in Ecole des Mines de Nantes (FR)

- Realisation of the event CRONET-DAYS in terms of contents (presentations of large projects in the mornings, and ONE to ONE meetings in the afternoons) as well as venue in Ecole des Mines de Nantes (FR) and official reception on the evening of the 28th April 2005, with 108 particpants.

- a CRONET-DAYS folder was provided to each participant: paper copies of morning  presentations, posters, copy of registration forms, practical information

- Further to response to a Post-event Satisfaction Questionnaire, the feedback from the participants appeared very positive.

- Recommendations were formulated for future similar initiatives

intentions for use and impact

Main results are in the CRONET-DAYS folder delivered to participants and in related e-documents available on www.sirehna.com . Main results for the participants included future collaborations as they were initiated during ONE to ONE meetings.